| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| Climate Action Plan | Sustainability in the Curriculum: Knowledge Systems: Recommend a definition of “Infusing Sustainability into Curriculum” using the work of the Faculty Senate Sub-Committee – Curriculum and Program Framework. | 11/19/2010 | Environmental Sustainability Steering Committee | The ESSC has recommended a definition for “sustainability in the curriculum” and has presented it to the Chancellor’s Cabinet. Members of the ESSC and the Sustainability Across the Curriculum Network (SACN) will present this definition to Faculty Senate, Senate of Academic Staff, and SSA during the spring 2011 semester. | The definition was presented to the Faculty Senate, Senate of Academic Staff (SAS), SSA, and Chancellor's Cabinet. The definition was endorsed by the Chancellor and SAS. It is slated for endorsement by the Faculty Senate in early fall. The definition and supporting material are available online in the UW-Stout Sustainability Across the Curriculum Network position paper. |
| Climate Action Plan | Sustainability in the Curriculum: Knowledge Systems: Provide campus with a list of potential classroom projects which were formulated from the energy conservation & waste reduction policies (i.e., student research, capstone projects, etc.). | 12/31/2010 | Environmental Sustainability Steering Committee | The ESSC has been working with the Sustainability Across the Curriculum Network (SACN) to compile a list of potential classroom projects related to energy conservation and waste reduction. The ESSC will provide this to the campus before the end of the fall 2010 semester. | The Sustainability website now includes a list of potential classroom projects for students. An online form enables people to suggest additional projects, which are then added to the list. Faculty and students who undertake a project are asked to notify the Sustainability Coordinator, who adds the project to an online list of implemented projects, providing a clearinghouse of what is happening on campus. |
| Climate Action Plan | Sustainability in the Curriculum: Knowledge Systems: Make available to campus a summary of action plans from the ‘Infusing Sustainability into Curriculum’ conference. A group from the ‘Infusing Sustainability into Curriculum’ conference would make recommendations to the Chancellor for campus wide academic initiatives. | 12/31/2010 | Environmental Sustainability Steering Committee | The ESSC has been working with the Sustainability Across the Curriculum Network (SACN) to compile a list of action plans from their ‘Infusing Sustainability into the Curriculum’ conference. The ESSC will make this available by the end of the fall 2010 semester. | ESSC and SACN compiled a list of action plans for infusing sustainability into the curriculum. The list is available online in the UW-Stout Sustainability Across the Curriculum Network position paper. |
| Climate Action Plan | Sustainability Policies: Management Systems: Review and evaluate environmental cost benefit analysis methodologies and recommend one that will be used to assess the proposed and actual impact of policy changes. | 12/30/2010 | Environmental Sustainability Steering Committee | The ESSC has reviewed cost-benefit analysis methodologies and recommended one, AASHE’s Sustainability Tracking Assessment and Rating System (STARS), to assess the impact of the energy conservation and waste reduction policies, as well as other areas of sustainability on our campus. | In December, the ESSC recommended that UW-Stout adopt STARS as its evaluation tool. The Chancellor approved the ESSC’s recommendation. For more information on STARS, refer to the UW-Stout Sustainability Across the Curriculum Network position paper. |
| Climate Action Plan | Sustainability Policies: Management Systems: Categorize or rank the components of each policy from near-term to long-term implementation. | 12/30/2011 | Environmental Sustainability Steering Committee | To date, the ESSC has not begun work on this charge. Once a cost-benefit analysis is completed, the ESSC will begin working on this. | The cost-benefit analysis will be conducted in May and is composed of two activities: desirability/feasibility ranking and detailed cost-benefit analyses. Qualtrics surveys have been developed to gather cost-benefit data and are currently in final draft form. Via Qualtrics, the ESSC and other key stakeholders will rank the desirability and feasibility of each component of the Waste Reduction and Energy Conservation policies identified as 3-Star policies by the ESSC. These data will be analyzed to determine the two most desirable/feasible waste reduction policies and the two most desirable/feasible energy conservation policies. Then, based on detailed cost-benefit data from the ESSC and other key stakeholders, the four selected policies will be ranked. The two most cost-beneficial policies will be recommended for near-term implementation and proposed to the campus. The other two policies will be recommended for mid-term implementation. Remaining policies will be recommended for long-term implementation. |
| Climate Action Plan | Sustainability Policies: Management Systems: Propose the policies incorporating the feedback from the campus. | 12/30/2011 | Environmental Sustainability Steering Committee | To date, the ESSC has not begun work on this charge. Once a cost-benefit analysis is completed, the ESSC will begin working on this. | ESSC plans to propose the policies selected via the cost-benefit analysis process (the two most desirable/feasible and cost-beneficial) during the Fall 2011 Listening Sessions. Susan Staggs will provide two discussion questions (one per policy) to Dr. Meridith Wentz, who will include these questions as discussion items during the Listening Sessions. Dr. Staggs has agreed to be a Listening Session Facilitator and will facilitate this process, as appropriate. Relevant data from the Listening Sessions will be captured and incorporated into the Climate Action Plan component of the UW-Stout Strategic Planning Process. |
| Climate Action Plan | Electronic Medical Records: Materials Management: Convert to electronic medical records to save paper and space. | 2011 | Student Health Services | No progress as of December 2010. Will implement the new system within 6-12 months. | Student Health Services (SHS) has been working with Vivature, a third-party billing vender, to introduce electronic records management in stages. For the first stage, SHS and UW-Stout IT are developing a program that captures student data from PeopleSoft and interfaces the data with Vivature software to support electronic records management. This May, SHS and IT will test the clinic scheduling program. Fall 2011, SHS plans to go live with both the scheduling program and electronic insurance billing. Within the next 12 months, SHS also expects to implement the secure student portal. Full implementation of electronic medical records will follow. |
| Climate Action Plan | Student Organization: Knowledge Systems: Establish the first student chapter of the Sustainable Agriculture in Education Association. | 2010-2011 | Collaborative | The Sustainable Agriculture in Education Association (SAEA) has worked with Kitrina Carlson and Sarah Rykal to allow us to establish the first student chapter of SAEA at UW-Stout. The group has become an official student group and meets regularly to work on sustainable agriculture-related issues. | The Sustainable Agriculture in Education Association (SAEA) meets regularly, works on sustainable agriculture-related issues, and promotes awareness within the community. This spring, the student group hosted speakers and cosponsored several Earth Week events. |
| Climate Action Plan | Alternative Transportation: Transportation: Promote transportation alternatives (StoutBikes, Dunn County Transit Bus Service, and UW-Stout RideBoard) to students, faculty, and staff. | 2010-2011 | Collaborative | We continue to promote alternative transportation on our campus. The StoutBikes program has been implemented and we continue to promote this in a number of ways. We are working with Dunn County Transit to have a bus route dedicated solely to UW-Stout, which we believe will be implemented in the spring 2011 semester. And we continue to promote the Rideboard, which is being used by a number of students, faculty, and staff at UW-Stout. | We continue to promote transportation alternatives in many ways, including the following. In partnership with Dunn County Transit, we offer a free shuttle service to any student, faculty or staff member with a university ID. We also offer an online RideBoard to students, faculty, and staff, which is frequently used. The StoutBikes program is underway, with interest growing. Periodically, Green Commuter Pledges are held, aimed at reducing the number of vehicle trips to and from campus. In addition, the Chancellor modified regulations to make rollerblading and skateboarding more attractive. The Chancellor also approved enhancements to bike parking areas, increasing the attractiveness of bicycling to campus. Plus, the ESSC/Parking will have a car-pool incentive program in place at the beginning of the fall semester. ESSC/Parking also plans to establish a staff walking/biking incentive program. |
| Climate Action Plan | Bike Share Program: Transportation: Implement the StoutBikes bike share program. | 2010-2011 | Collaborative | The StoutBikes program, a collaborative effort with Parking Services, the Cycling Club, and Physical Plant, was implemented in the fall 2010 semester. | Many students participate in the StoutBikes program, which is administered by Keith McCarten of Parking Services and the ESSC. Pete May of BadCat bikes has renovated additional bikes, bringing the bike count to about 30. |
| Climate Action Plan | Bottled Water Consumption: Materials Management: Implement an “I Love Tap Water” campaign to reduce bottled water consumption on campus. | 2010-2011 | Environmental Sustainability Office | The Environmental Sustainability Office and ESSC are working with marketing students to create the “I Love Tap Water” campaign. | The logo was approved for use on posters, the website, water bottles, and other advertising materials. Amy McGovern worked with designers to put together promotional materials. Krista James’ Bio 111 class distributed materials in the Menomonie community. Julie Xenos ordered water bottles for sale at the bookstore. |
| Climate Action Plan | Energy Conservtion: Energy Management: Implement the “Biggest Reducer” Energy Conservation Campaign to reduce energy consumption and waste on campus. | 2010-2011 | Environmental Sustainability Office | The Environmental Sustainability Office is working with marketing students to develop the “Biggest Reducer” campaign and hopes to implement the campaign in spring 2011. | Supporting brochures, posters, presentation, and score cards have been developed. However, implementation is on hold. |
| Climate Action Plan | Locally Produced Foods: Materials Management: Work with Producers & Buyers Cooperative to purchase more local food. | 2011 | Dining Services | Dining Services plans to work with Producers & Buyers Cooperative starting in January 2011. In October 2010, Dining Services hosted a local food dinner called the “Midwest Harvest Buffet.” The event was attended by 1082 diners at Price Commons and 543 diners at North Point. | In January, 2011, Dining Services began meeting with the new Director of the Producers & Buyers Cooperative and plans to process paperwork for membership over the summer. |

13 action plan items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| University-Wide Training and Development Plan | Leadership and Professional Development Program. |  | Director of Human Resources | 1 employee of UW-Stout currently attending Leadership Menomonie | The ASLS division plans to encourage participation for 1-2 employees for the 2011-2012 year. |
| University-Wide Training and Development Plan | Fiscal Services, Enrollment Services, Administrative Services, University Services. |  | Director of Human Resources | 3 EDGE sessions completed and 9 sessions schedule for 2011. | A total of 12 EDGE sessions were held with an average of 15 attendees per session. |
| University-Wide Training and Development Plan | Campus business operations training. |  | Director of Business & Financial Services | EDGE sessions scheduled for 02/01/11, 02/15/11, 03/01/11, 03/29/2011, and 04/12/11 | EDGE Sessions held on 02/15/11, 03/01/11, 03/29/11, 04/12/11, 04/19/11 and 04/26/2011 about the following topics: Materials Management, Vendor and Purchasing Contracts, Accounts Receivable, Travel/General Ledger/Accounts Payable, Duplicating and Printing, and Budget/Internal Audit. |
| University-Wide Training and Development Plan | Personal development/interpersonal relationships (ex. smoking cessation) |  | Optimal Health committee | We held a “Discovering Wellness” night in Nov. open to the entire campus community. The importance of staying healthy in all areas of the wellness wheel was stressed. Organizations that students can get involved with in hopes to help curb the alcohol abuse issues we have on campus were promoted. The event was a success and saw lots of traffic. | The 11th annual health fair, was on Wednesday, April 6th. There were 31 vendors (4 who were brand new this year) and a total of 552 attendees. |
| University-Wide Training and Development Plan | Department Chair Training |  | Provost; Director of Human Resources | New Department Chair Orientation held on 09/03/10 with 6 new Chairs and Deans in attendance; 3 all Department Chairs training sessions held: 09/01/10 Public Records/Open Meeting and Employment Issues 25 in attendance; 09/02/10 Recruiting and Retaining Minority Faculty and Staff 18 in attendance; 11/24/10 Establishing Performance Expectations and Coaching 16 in attendance | 1 all Department Chair training session “Performance Management and Performance Reviews” held on January 19, 2011 with 14 attendees. |
| University-Wide Training and Development Plan | Program Director Training |  | Provost, Director of Human Resources | New Program Director Training held on 09/02/10 with 31 in attendance; Regular meetings held with program directors facilitated by Provost's Office, Dean of Students, Executive Director of Enrollment Services and Registrar. Degree audit training provided to program directors in the fall of 2010 | Regular meetings held with program directors facilitated by Provost's Office, Dean of Students, Executive Director of Enrollment Services and Registrar. |
| University-Wide Training and Development Plan | Train faculty & staff on how to effectively incorporate student experiential opportunities into programs and curriculum (broaden horizons) |  | Provost; NTLC | In Progress - This training is currently being provided by other offices on campus including Career Services and the Office of International Education | Ongoing - This training is currently being provided by other offices on campus including Career Services and the Office of International Education. In addition, the NTLC incorporates training related experiential learning in most faculty development programming. |
| University-Wide Training and Development Plan | Baldrige Training, Assessment and Evaluation, and AQIP |  | Provost; Director of Human Resources | Baldrige Training provided to CAC; AQIP Strategy Forum attended by UW-Stout Team; program assessment training provided by colleges | UW-Stout team attended AQIP Training at the Higher Learning Commission Conference in April. Assessment consultant from ACBSP came to UW-Stout to work with faculty members in preparation for accreditation. Provost's Office and NTLC will offer two summer institutes, one on program assessment (with Susan Hatfield as facilitator) and one on credit for prior learning. |
| University-Wide Training and Development Plan | Quality Training Certificate (quality tools) |  | Director of PARQ; Director of Human Resources | There were 13 attendees at the fall training session, “Using Quality Tools”. Using a 4-point evaluation scale, attendees evaluated the session. Value in current position: 3.57 Value to UW-Stout employees: 3.71 Increase in subject knowledge: 3.54 Comments about the session included: “I would like to see department chairs, deans, etc (whoever runs a meeting) to have this training” and, “Never had such a great training session on this. Thanks.” | Two sessions were held for Spring training, led by Jeff Russell of Russell Consulting, Inc. "The Fundamentals of Project Management" had 25 attendees and "Understanding and Managing Conflict" had 18 attendees. |
| University-Wide Training and Development Plan | Customer service |  | Director of Human Resources | National Customer Service Week was celebrated 10/04-10/08/10 with candy delivered to departments, reception and two breakout sessions: “In the Happiness Business” and “When you have Lemons, make Lemonade” with 60 + in attendance. | “Discovering Common Ground” presentation held on January 20, 2011 with 22 attendees. |
| University-Wide Training and Development Plan | ADA: Awareness, competence and procedures for employee accommodation requests |  | Director of Human Resources | Presented during 08/31/10 and 12/07/2010 New Employee Orientation | Presented during the January 19, 2011 New@UW-Stout Orientation Program. |
| University-Wide Training and Development Plan | Equal Employment Opportunity (race/ethnicity/disability/gender/discrimination/harassment) |  | Director of Human Resources | Presented during 08/31/10 and 12/07/2010 New Employee Orientation | Presented during the January 19, 2011 New@UW-Stout Orientation Program. |
| University-Wide Training and Development Plan | LGBTQ |  | LGBTQ Coordinator | 4 Safe Space Trainings for faculty, staff and students this fall. The 90-minute trainings were held on September 23, October 13, October 21 and November 3. Offered 6 training sessions for Counseling Center staff and faculty/students from Stout’s counseling-related graduate programs (Mental Health Counseling, School Counseling, Marriage and Family Therapy and School Psychology).The training focused on best practices in working with bisexual students/clients. | No updates. |
| University-Wide Training and Development Plan | Faculty/Staff Complaint Process |  | Director of Human Resources | Presented during 08/31/10 and 12/07/2010 New Employee Orientation | Presented during the January 19, 2011 New@UW-Stout Orientation Program. |
| University-Wide Training and Development Plan | Student complaint process |  | Dean of Students | The offices that are responsible for tracking complaints have been trained in fall 2010 on the web-based reporting form. | No further update, however, plans are in place to more distribute information on procedures for various types of complaints to be implemented by fall 2011 |
| University-Wide Training and Development Plan | Academic and non-academic misconduct |  | Dean of Students | Dean of Students provided training for Department Chairs in Fall 2010 and will provide to new instructors through NTLC in Fall 2011. Dean of Student website provides additional information for faculty/staff regarding UWS Ch. 14 academic misconduct. | Will continue to provide training for incoming faculty. |
| University-Wide Training and Development Plan | FERPA |  | Dean of Students | Dean of Student provided training to Department Chairs and Student Services offices in fall 2010. | Put more information on Dean of Students website, provided resources to NTLC for faculty training and distribution. Information was also presented during the New@UW-Stout Orientation Program on January 19th, 2011. |
| University-Wide Training and Development Plan | Ethics |  | Chancellor | Presented during 08/31/10 and 12/07/2010 New Employee Orientation | Presented during the January 19, 2011 New@UW-Stout Orientation Program. |
| University-Wide Training and Development Plan | PeopleSoft |  | Unknown | $2,000 has been allocated for student help to implement data queries and provide training to faculty and staff for PeopleSoft access. | Data custodian training has begun. End user training beginning Summer 2011 |
| University-Wide Training and Development Plan | Outlook E-mail |  | CIO | In progress - Provided online through Lynda.com | In progress |
| University-Wide Training and Development Plan | Microsoft Office Suite/PowerPoint |  | CIO | In progress - Provided online through Lynda.com; Excel Training class offered Nov – 2nd, 9th and 16th with 24 attendees. 3 open lab session offered on Nov. 4th, 11th, and 18th with an average of 6 attendees. Another Excel class will be offered during 2nd semester. PowerPoint will also be offered 2nd semester. | In progress - Provided online through Lynda.com; Excel Training class offered Feb 22nd -March 8th with 22 attendees. 3 open lab sessions offered on Feb 23rd, March 2nd and 9th with an average of 5 attendees. PowerPoint Training class offered April 5th – 12th with 21 attendees. 2 open lab sessions held on April 7th and 14th with an average of 5 attendees. |
| University-Wide Training and Development Plan | Qualtrics (On-line survey and course evaluation tool) |  | PARQ | 82 people received 1:1 Qualtrics assistance from July 1, 2010 through December 6, 2010. Additionally, during the same time period, 7 training sessions were held with 38 attendees and 17 webinars were shown with 13 attendees. | 135 people received 1:1 Qualtrics assistance from December 1, 2010 through April 22, 2011. Additionally, during this same time period, 6 training sessions were held with 66 total attendees. |
| University-Wide Training and Development Plan | Hyperion |  | CIO | Training is coordinated through the DoIT Training Center if campus-based training is needed. Otherwise individuals attend the training sessions offered at UW-Madison. Periodic preview sessions are held on campus on developed campus queries. These are based more on data delivered in the queries. | Scheduled as needed |
| University-Wide Training and Development Plan | Software applications including Adobe Acrobat , Photoshop, Dreamweaver |  | CIO | In progress - Provided online through Lynda.com | In progress |
| University-Wide Training and Development Plan | Adobe Connect (formerly Breeze) |  | CIO | Provided Fall 2010, January 2011 | Adobe Connect licensing expired. UW System now licensing Elluminate. |
| University-Wide Training and Development Plan | Echo 360 (formerly Apreso) |  | CIO | Provided Fall 2010 New lecture capture system in January 2011 | Tegrity new supported lecture capture. Training being scheduled |
| University-Wide Training and Development Plan | Common Spot |  | Integrated Marketing Director | Training documentation is online at: http://www3.uwstout.edu/webdev/commonspot_help.cfm. Open labs: 8 Training sessions: 12 | Training documentation is online at: http://www3.uwstout.edu/webdev/commonspot_help.cfm. Open labs: 6 Training sessions: 4 |
| University-Wide Training and Development Plan | Training for CI/DE instructors |  | Stout Online & LTS | In Progress – Webinar - 10/18/2010 - "Helping Faculty Manage Online Workload" CD - 10/19/2010 "Teaching Online vs F2F: 15 Differences That Affect Learning" | 1/28/11 Webinar: “Universal Design” Summer Institute scheduled for June. |
| University-Wide Training and Development Plan | New Instructor Workshop |  | Director of Teaching & Learning Center | Held on August 17-19 2010, with 33 attendees. | Fall 2011 New Instructor Workshop will be offered August 16-18, 2011. |
| University-Wide Training and Development Plan | New Employee Orientation (including diversity training) |  | Provost; Director of Human Resources | 2 sessions held 08/31/10 with 19 in attendance and 12/07/2010 with 8 in attendance. | 1 session held on 01/19/2011 with 10 attendees. A session will be scheduled in late May. |
| University-Wide Training and Development Plan | EAP training |  | Director of Counseling Center | Presented during 08/31/10 and 12/07/2010 New Employee Orientation by Jeanne Rothaupt, Ph.D., Employee Assistance Program Coordinator and John Achter. | Presented during the 01/19/2011 New@UW-Stout Orientation Program. |
| University-Wide Training and Development Plan | Workplace Violence Prevention |  | Executive Director of Health & Safety | On-going through UW-Stout Police | Sessions were held in spring semester 2011 |
| University-Wide Training and Development Plan | Asbestos compliance/overview |  | Executive Director of Health & Safety | Between the Physical Plant and Health and Safety Units, there are 7 asbestos inspectors and 5 asbestos supervisors. It is anticipated that there will be 8 asbestos inspectors and 6 asbestos supervisors following the certification of the Crafts Supervisor in 2011. 136 employees received asbestos awareness training and 57 employees received asbestos O&M training. Refresher training will be provided in January 2011. | Asbestos O&M training was held in February and asbestos awareness training was held in March. 24 ASLS supervisors and 1 lab manager participated in a Workplace Safety and OSHA compliance training session on April 29, 2011. |
| University-Wide Training and Development Plan | Lead compliance/overview |  | Executive Director of Health & Safety | Physical Plant asbestos competent person is also the lead contact – ongoing. | No activity. |
| University-Wide Training and Development Plan | Defibrillator training |  | Executive Director of Health & Safety | Stout Police offers this as needed, usually with CPR | Training for Student Health and Physical Plant will be held in May, 2011 |
| University-Wide Training and Development Plan | Emergency Management (including building evacuation, alarm codes, etc) |  | Executive Director of Health & Safety | Offered at quarterly new employee orientation, and annual Student RA / Hall Director training | COOP training session scheduled for May 4th, 2011 |
| University-Wide Training and Development Plan | Identifying students and co-workers at risk |  | Dean of Students | Information is sent to all faculty/staff each fall semester on the Students of Concern/risk assessment signs, process of informing the SOC team, and other threat assessment information. All SOC and faculty of concern team members have been trained extensively in Threat Assessment and response. | Information will continue to be sent to all faculty and staff each fall semester. Same as 6 month update. |
| University-Wide Training and Development Plan | Fire extinguishers |  | Executive Director of Health & Safety | Offered annually by Safety & Risk Management for Physical Plant and Dining | Training due in October 2011 |
| University-Wide Training and Development Plan | Ergonomic workstations |  | Executive Director of Health & Safety | Offered as requested. Infrequent demand. | No activity |
| University-Wide Training and Development Plan | Provide training to data leads on how to obtain data from central databases |  | Pam Holsinger-Fuchs and Assistant Registrar | Scott Correll has been hired as registrar. Names of data leads from campus have been received. Training will occur this summer. LTE will start Jan. 3 to respond to data requests in the interim. Central data request form is being developed for consistency. $10,182 has been allocated for LTE funding to assist in responding to data requests. | First training was held on April 26th. Summer training is scheduled for July 18-21st with super users and others. There are currently 30 staff that have been designated as data leads. Josh Lind, Assistant Registrar has been hired to lead this project. |

40 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| High Risk Drinking Prevention Plan | Support faculty/staff in required class attendance. EAC review UW-Stout attendance policies/guidelines. | Fall 2010 | Faculty Senate Abel Adekola | EAC reviewed Attendance Policy and recommended revisions are before the Faculty Senate. | Approved by EAC on 10/11/2010 1. Regular attendance is the responsibility of each student, and it is assumed that students will attend all classes for which they are enrolled. 2. The attendance policy of each instructor is to be submitted in writing to each student at the beginning of the course. It may be discussed with or explained to the students. Attendance is likely to affect the student’s achievement and it is at the instructor’s discretion as to how class attendance and participation are factored into the student’s overall grade for the course. |
| High Risk Drinking Prevention Plan | Increase number of classes held on Fridays. | Fall 2010 | Provost | Friday classes for Fall 2010 were increased by 20% | Spring 10 = 392 classes that had a meeting on Friday Spring 11 = 544 classes that had a meeting on Friday Increase of 152 or 38%. |
| High Risk Drinking Prevention Plan | Implement consistent enforcement of policies across campus for students who engage in high-risk alcohol behavior that threatens harm to self or others, results in criminal charges or property damage. | Fall 2010 | Dean of Students Office/Housing | Dean of Students Ch. 17 Conduct Cases 9/6/2010 – 11/30/2010. 247 alcohol related cases investigated resulting in: Disciplinary probation – 50 Suspensions – 15 Expulsion – 2 Warning – 88 Other – 13 Housing conduct policy also sanctions students who do not rise to the level of UWS Ch. 17 | Dean of Students Alcohol Conduct Cases 9/1/10 – 4/30/11: 639 total alcohol related cases (includes 332 Housing policy cases which did not rise to Ch. 17 level) investigated resulting in following Chapter 17 sanctions: Disciplinary Probation – 104 Suspension – 37 Other Ch 17 Sanctions – 82 Ch.17 Warnings – 122 Increase in Ch. 17 sanction in 2010-11 from 2009-2010 – 658% |
| High Risk Drinking Prevention Plan | Collaboration with local agencies (Arbor Place) and law enforcement to support more frequent party patrols and strong sanctions for hosts. | Fall 2010 | Lisa Walter | 22 deployments – party patrols, party mapping, beat patrols, bar checks, and bar walk-throughs. Trained 35 officers and community volunteers. New member training/orientation scheduled for Jan. 27th | 11 party patrols, there will be 13 total by the end of the academic year. So far we have issued 123 citations. We have had significant increase in awareness and visibility and there is belief that deployments have had an impact on reducing party house sizes. |
| High Risk Drinking Prevention Plan | Parental notification when students engage in serious or repeated violations of alcohol policies and/or the law. | Fall 2010 | Judicial Officers Joan Thomas | 65 students have had their parents contacted regarding alcohol policy violations. | For period 9/1/10 – 04/30/11 there were 261 parental contacts for alcohol related policy violations, broken down as follows: Dean of Students letter – 33 Housing letter – 123 Housing phone call – 105 |
| High Risk Drinking Prevention Plan | Ban the promotion or marketing of alcohol and/or drinking by eliminating “drinking related” items in campus stores (Niche, bookstore) in classroom projects and in published materials. Refrain from hiring comedians, etc. that support a culture of drinking during New Student Orientation – Week One. | Fall 2010 Ongoing | Provost University Relations Kim Nimsgern | Niche, Marketing Class, bookstore were contacted. Comedians and performers on campus either avoided or provided positive messages | New Student Orientation will not include/promote any programming that normalizes a culture of drinking. In addition, the “alcohol statement” will be included in the Orientation booklet along with social norms campaign materials. All incoming first year students will be expected to attend the “Flash Your Smart Card” program which focus on making responsible choices. |
| High Risk Drinking Prevention Plan | Support changes in City Ordinances related to environmental change, especially the pursuit of “Public Intoxication” citation. | Fall 2010 | Jacob Bloom Campus Admin | Intoxicated server went before City Council was voted down 7-4. Three City Council members attended December Coalition meeting with plans for collaboration and information sharing. There is a new motion to review fines and alcohol licensing and renewal process. | Public Intoxication ordinance was passed unanimously by City Council on April 18th, 2011. |
| High Risk Drinking Prevention Plan | Educate students on the impact of alcohol violations/behaviors may have on educational/career choices, study abroad opportunities, conference participation, employment potential, and other goals and opportunities. | Fall 2010 | Mary Hopkins-Best Joan Thomas | Mary authored a document that was provided to deans, shared with PD, and used extensively in Career Services and other Student Services offices and program titled, “The Effects of Alcohol and other Drugs on your Professional Identity.” | No update. Will continue to emphasis in this area next fall through same efforts. |
| High Risk Drinking Prevention Plan | Communicate alcohol policies, sanctions, and procedures to campus and provide advance notice of possible sanctions for high risk and/or repeated behaviors. | Fall 2010 | Joan Thomas | Provided “Enforcement Plan” document to all students fall. | Will present information during Freshmen registration and new student orientation summer/fall 2011. |
| High Risk Drinking Prevention Plan | All first year students will take e-Chug during the spring term prior to registration. (HOLD on registration until completed). | Spring 2011 | Jake Bloom Joan Thomas Scott Correll | Contacted e-chug and had the software changed to provide email verification once a student completes program. Created e-chug email account. Verification of completion emailed to Jake Bloom – contact person. Next steps are integration with IT, Registrar and Advisement Center to set up “registration hold” until completed. | Plans are in place to implement E-chug requirement for all first year students prior to spring 2012 registration. Collaborative effort with IT, Registrar, and Advisement Center. Counseling Center and Housing currently use e-Chug with certain segments of the student population to help assess alcohol use. |
| High Risk Drinking Prevention Plan | Involve students in education regarding alcohol – target groups such as athletics, SSA, Greeks, Student orgs. | Fall 2010 | Jake Bloom | Wrote 2011 DOT grant to engage students as partners (funded at $5,000) Student hired to network with target groups on campus. MSS, Athletics, Res Life, UREC, MSS are collaborating to deliver AOD outreach to their peers. Athletics in beginning stages of “Step-Up” program for bystander intervention. Developing AOD Education Curriculum to be implemented via peer to peer on following topics: BAC education, underage fines and consequences, bystander intervention, alcohol facilitated sexual assault. SSA is developing a prevention video and passed resolution on alcohol initiatives they will partner on and support. | Hired several students who developed and presented numerous outreach presentations to target groups on the topics BAC education, alcohol facilitated sexual assault, and bystander intervention. Campus Display Cases (25) – on the topics of Alcohol Facilitated Sexual Assault and Bystander Intervention. Participated in the campus Health Fair & Housing’s Wellness Expo. In process of creating scripts for freshmen orientation video segments. Finalizing DOT Grant curriculum manuals for student use. DCPFY – The Plunge – assisted with bus tour – participation by dean of students, Stout police chief, asst. dean of students and AOD coordinator. Athletics “Step Up” bystander program. Have done a pilot study with a smaller group. Initial feedback is very good, Have some tweaks to the situations we will go through. Plans are for 100% rollout with all student-athletes in the fall of 2011. Dates are set. SSA Video has videotaped some segments and video should be ready for fall 2011 implementation. |
| High Risk Drinking Prevention Plan | Send letter to incoming freshman and their families prior to fall term regarding Stout’s philosophy and expectations for keeping students safe. Signed by Chancellor, Dean of Students, Chief of Police, Alcohol Coalition Chair. | Fall 2010 | Joan Thomas | Letter went out to all families of incoming freshmen signed by those identified. | No Update. Will do again fall 2011. |
| High Risk Drinking Prevention Plan | Develop, implement, and infuse campus wide alcohol philosophy statement throughout campus – publications, websites, letters, etc. | 2010-2011 Ongoing | Joan Thomas | Website is up to date with education and prevention materials and the alcohol plan. http://www.uwstout.edu/aod/index.cfm Alcohol philosophy statement was also in the new student Orientation booklet. The University of Wisconsin Stout will strive to create and support an environment where use of alcohol does not prevent students from realizing their highest potential of intellectual, physical and human development. The University will use evidence based policies, programs, and services and will assess progress through measurable goals and objectives. | The “alcohol statement” will be included in the Orientation booklet along with social norms campaign materials. |
| High Risk Drinking Prevention Plan | Incentive for students who do not get an alcohol violation in their first year. (Blue Devil T-shirt?). | 2010-2011 | Joan Thomas | In progress – incentive not identified. | Will work on this for upcoming year. Will query all first year students who do not have a conduct matter in Maxient and are enrolled for sophomore year. |
| High Risk Drinking Prevention | Development and implementation of the Housing Alcohol Plan for 2010-2011. | Fall 2010 | Scott Griesbach | Infusing alcohol messages – Life @ Stout, bulletin boards, Smart & Healthy Campaign, RA dialogue, housing programs addressing alcohol issues. | See attached. Extensive High Risk Drinking Prevention plan was implemented by Housing in 2010-12. |
| High Risk Drinking Prevention Plan | Social Norms meeting campaign, chair Chancellor’s Coalition on Alcohol and Drugs, participation on UW System AOD committee, collaboration with Dunn Country Partnership for Youth, Dunn County Alcohol Task Force, administration of DOT grant, training conduct staff in motivational interviewing, alcohol assessments, and other aspects of the Alcohol Plan. | Fall 2010 Ongoing | Joan Thomas | UW System AODA Committee: System AOD Use Survey – spring 2011 Campus Community Readiness Assessment meeting – Feb. 3 and 4 Dunn County Youth Partnership Presentations: Lions Club, Kiwanis, SSA, Optimist Club, Mainstreet Menomonie, etc. Support for ordinance changes. Media Campaign/Public Awareness with Face Project “Domino Strategy” and bathroom readers in local establishments. Dunn County Area Task Force (DCATF). Update under collaborations | UW System AOD Committee: System AOD Use Survey administered in February 2011. Attended Campus Community Readiness Assessment Training (AOD coord. and asst. dean of students). |

16 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| Inclusive Excellence Plan | Marketing materials: Produce DVD/video for parents, counselors and on web, make marketing materials amenable to all diverse groups, web materials need to be accessible to diverse students. | May 2011 | Executive Director of Enrollment Services and Marketing Director | Working with a committee and outside vendor to produce 4 to 5 videos for targeted audiences. Meeting was held with steering committee. Six separate videos are being planned focusing on: African-American, LGBTQ, Hmong, Latino/Hispanic, Native American and students in non-traditional roles. The videos will be web streamed not produced on a DVD for easier distribution. | 7 videos will be completed by June 30th focusing on the following target audiences: African-American, Hmong, American Indian (First Nations), Latino/Hispanic, LGBTQ, Veteran/Military Service member and students in non-traditional roles. The videos will be linked off the Admission & MSS website and will also be in a rotation off the Stout homepage after the web redesign. |
| Inclusive Excellence Plan | Diversity population-specific (minority, disabled, LGBTQ, women in non-traditional areas) recruiting – with people who can build relationships with diverse groups. To facilitate this, engage student leaders on campus and alumni in recruitment process. | Plan received by January 2011 | Executive Director of Enrollment Services, Alumni Office, MSS Director, Pride Alliance, Dean of Students | Coordinate ethnic specific campus visits for prospective students in collaboration with student organizations. Native Pride at UW Stout (with NASO-10/14/10), BSU(March), HSSO (April) Latinos Unidos (March). Collaborated with Admissions – “Route to Stout” campus visit for Eau Claire high school (Hmong) students. Attend college fairs with significant diversity populations (MN, LCO, College Explosion, WEASSP, Milwaukee Precollege) Develop partnerships with federal educational grant programs to promote precollege participation. (Spring 2011). Develop MSS precollege web page with online communication to include prospective and current students and alumni. (Spring 2011) Contact with Veteran Drill Halls in Spring 2011. Veteran marketing materials. Separate groups are being formed for each of the six targeted groups listed above. Disabled student recruitment will not be a focus due to the challenges of funding for services. SSA is involved to engage students of color in the recruitment process. Alumni of color will be engaged through work with the MSS office. | Admissions coordinated campus visits for 599 ethnic minority students. Admissions and Multicultural Student Services collaborated with student organizations to host campus visits for under-represented minority students. 30 American Indian students-Fall 2010 130 Hmong students –Spring 2011 Anticipate 60 Latino students-May 2011 (BSU event cancelled due to staffing shortage in MSS and BSU reorganization) Somali student event was held in conjunction with the Multicultural Education class. Several phon-a-thons to outreach to alumni were held but problems ensued due to incorrect contact information. Alumni that were contacted are going to be part of a resource network for future collaborations. Attendance at state GEAR UP conference of staff from Admission and MSS to establish and strengthen networking relationships. Attended all proposed college fairs with significant diversity representation. Frequent communication with UW Stout Talent Search and Upward bound to promote PreCollege participation. |
| Inclusive Excellence Plan | Admissions will follow up with multicultural students with incomplete applications to offer additional assistance and Multicultural Services will contact new admits. | Sept 2010 | Executive Director of Enrollment Services for apps, MSS Director for admits | MSS staff initiates personal phone calls and provides mailings to multicultural student admits. Calling of all prospective and applicant students of color has been occurring during the fall. Admitted students are being followed up with by the MSS staff. A separate mailing also went out to all of the students of color from our Multicultural recruiter. Student telerecruiters will also be calling on March 7 & 10th as well for follow-up questions. | Student tele-recruiters called students of color over two separate weeks in the spring. The multicultural recruiter continues to follow up with specific students. A barrier that exists is for students to pay for their housing deposit that are low-income in contrast to other UW schools. MSS staff and students have on-going calls with all of the admits. All admits receive literature from admissions and MSS. |
| Inclusive Excellence Plan | Broaden definition and formalize pre-college process. Every student attending receives the same resource materials about UW-Stout. Use pre-college as recruitment tool with more comprehensive follow-up and tracking of students who participate. Explore external funding to expand pre-college programs for targeted groups. | Plan by January 2011 | Executive Director of Enrollment Services; Dean of Students; Camps and Conference Coordinator | Bulletin boards, table tents and information was created for the summer camps and admissions viewbooks placed in each residence hall room for the summer of 09-10. In addition a presentation was provided for each pre-college program about Stout. A letter was designed for all pre-college students by a former pre-college participant that is a current Stout student. All of the pre-college student data has been added to our prospective database in RP. A replication grant was submitted for the People Prep program and was not funded. Additional grants are being considered. | ASLS: Student Life Services – We continue to focus on maximizing the use of all campus space through our centralized scheduling initiative. Outreach will continue with summer camps that currently bring their programs to UW-Stout. An opportunity exists for the campus to expand our camps for high school students as a recruitment effort. |
| Inclusive Excellence Plan | Targeted approach to reach parents of middle school and high school students, utilize parent/teacher associations, target school districts, use websites to reach these audiences. | Plan by January 2011 | Marketing Director; Executive Director of Enrollment Services; MSS | DPI Precollege grant proposals for three (3) - one week, residential summer programs were submitted and expect notification in January. Develop partnerships with Eau Claire, Menomonie and Wausau schools to offer college preparation opportunities. Informational workshops will be available for parents/families, community organizations, educational programs and schools. Precollege web page will be enhanced with video clips by students and staff to include Hmong and Spanish for parents with limited English. (Spring 2011) Working on targeted plan to reach various targeted audiences with Enrollment Management Director Mall Kiosk has been designated for Oakwood Mall with a specific marketing piece for distribution to parents/students | Meetings were held in Abbotsford with Hispanic/Latino students, parents and school staff. (Stout student serving as liaison) This approach will be emulated in the future with other communities of color. A VISTA/AmeriCorp position was funded and will start next year with targeted outreach to Hmong and Hispanic/Latino students and parents. A State Farm grant is being submitted to target Hmong families about higher education. Three new state grant PreCollege (each one week summer residential) programs funded. Partnerships in local schools, Stout federal funded precollege and Gear Up programs help recruit a diverse student population. PreCollege brochures, applications and video clips available in Spanish and Hmong for student families. (5 month staff vacancy in PreCollege) |
| Inclusive Excellence Plan | Re-establish an ESL program. | June 2011 | Director of International Education | Received final approval for establish ESL program on 12/1510. I am planning to hire a curriculum developer in January. I am also working with UG admissions, graduate admissions, records and registration and Cashier’s office to set up the Peoplesoft system to accept ESL students. Due to the unexpected delay in approval process, we have to postpone the program starting date to Fall, 2011 as our current computer system is not ready. | No response received. |
| Inclusive Excellence Plan | Provide mentorship for students of color with other student leaders, faculty, staff and alumni. | May 2011 | MSS Director | Two (paid) peer mentors encouraged students to utilize campus resources, participate in MSS activities, facilitated workshops to promote academic success and created opportunities to enhance campus climate through social activities and student organizations, utilized bystander intervention strategies within the Springboard and Stoutward bound living and learning community. Mentors maintained communication through phone, text, email, facebook and personal contacts. Five additional mentors will be hired Spring 2011 to expand services and utilize on-line format to connect with alumni and invite faculty to offer encouragement to students with “monthly lunch conversations” in MSS. | Six (paid) peer mentors offer consistent outreach to students by coordinating workshops and meeting with students in MSS. Mentors offer numerous opportunities (in person, electronic, phone) to promote academic success and student involvement. Significant collaboration with student organizations, faculty and staff is ongoing with increased participation. Two lunch conversations were held with Minority Faculty Staff Network to offer support to students. |
| Inclusive Excellence Plan | Empower multi-cultural student organizations that target diverse populations with additional advisement support. | May 2011 | MSS Director | MSS staff serves as Advisors to BSU, HSSO, Latinos Unidos and NASO. MSS staff attend meetings, organization activities and regularly meet with student leaders and SSA Diversity Director to enhance cultural identity development, collaboration and leadership. | ALL MSS Staff are actively and regularly empowering student organizations with significant improvement in participation, leadership and collaboration. |
| Inclusive Excellence Plan | Increase use of SAGE program to identify students who are experiencing difficulties early in their academic careers. | January 2011 | Dean of Students, Academic Deans | Pilot in spring 2011, full implementation fall 2011 | Dean of Students: Due to change in director for Advisement Center, this activity is postponed to fall 2011. Will pilot fall 2011 after new director arrives in Advisement Center. CEHHS: Our faculty and staff have not yet been oriented to this program |
| Inclusive Excellence Plan | Develop ways to enhance students’ lives outside of the classroom – including in the community, expand civic engagement model/VISTA program, and service learning opportunities. | May 2012 | Assistant Vice Chancellor (ASLS) | Ongoing – Coordinator of Civic Engagement has been hired this month. This person will lead the establishment of an advisory group to pull community, faculty and student together. | ASLS: The development of the Civic Engagement Model is on-going. We are working on developing two more grant proposals for VISTA volunteers; we submitted a grant proposal for a number of MC3 scholars; we are making connections with area leaders and connecting them with students. We should have a complete civic engagement outreach program established in one year. |
| Inclusive Excellence Plan | Continue to support and expand Bridge programs in the summer. | Sept 2011 | Dean of Students | In progress…external funding needed, Great Lakes grant supported some funding last year, but it is uncertain for 2011. Will continue to seek outside funding options. | Dean of Students: Submitted UW System Growth Agenda grant. Will fund 2 Bridge programs of 25 students each for fall 2011 from 402 funds. Enrollment is near full as of 5/1/2011. Two Bridge programs for summer 2011 to enroll 50 students – almost full. Could expand if we had additional funds to pay room and board costs. |
| Inclusive Excellence Plan | Expand learning communities with attention to targeted populations. | See University Priority | See University Priority |  |  |
| Inclusive Excellence Plan | Review retention and graduation rates for each undergraduate program and make plans for improvement as needed. | Plans by May 2011 | Academic Deans; Undergraduate program directors; BPA Director | COM: Request initiated. Review in process. STEM: Information on undergraduate program retention and graduation rates received 12/07/10. Review to begin in January. CAHSS: We are prepared to review the retention and graduation rate data, provided by PARQ, for our undergraduate programs. PARQ: Program facts will be provided to Deans early second semester. | PARQ: Program Facts documents were provided to all deans in December, 2010 STEM: Consider curricular changes, elective/selective reductions, and scheduling cycles toward 120 credit programs Submit program course learning objectives to departments for development of systematic assessment Identify and resolve scheduling conflicts in required program courses CAHSS: Final draft of the “plan” to be submitted to Inclusive Excellence committee on May 13, 2011. CEHHS: The dean has met individually with each undergraduate program director to review the retention and graduation rates. Programs with rates lower than the university average have established specific strategies. Examples that have resulted in increased retention and graduation rates include: BS Dietetics revised the web site with more program specific expectations; BS FCS published a specific course sequence; a new program director was hired for the BS Art Education; the PD of the BS TE has arranged high school visits at high schools with high percentages of diverse students. Other retention initiatives have included developing new learning communities for CEHHS students and offering a summer bridge program for underrepresented education majors. |
| Inclusive Excellence Plan | Review retention and graduation rates for each graduate program and make plans for improvement as needed. | Plans by May 2011 | Academic Deans; Graduate program directors; BPA director | COM: Request initiated. Review in process. STEM: Awaiting data on retention and graduation rates for graduate programs. CAHSS: We are prepared to review the retention and graduation rate data, provided by PARQ, for our graduate program. PARQ: Program facts will be provided to Deans early second semester. | STEM: Review audiences and student goals for customized programs to determine expectations for retention and graduation rates, particularly involving part-time, non-traditional students CAHSS: Final draft of the “plan” to be submitted to Inclusive Excellence committee on May 13, 2011. CEHHS: The dean has met individually with each graduate program director to discuss graduation rates. The most common reason for students not graduating is completion of the research requirement. Examples of initiatives to improve graduation include a program revision to incorporate an applied research experience within a capstone course and a program revision to provide students a choice of a comprehensive exam or a thesis. |
| Inclusive Excellence Plan | Review pass rates in courses and make plans for improvement as needed. | Plans by May 2011 | Academic Deans; Department chairs; BPA Director | COM: Request initiated. Review in process. STEM: Data on pass rates in larger enrolled STEM courses forthcoming. Review to begin upon receiving data. CAHSS: We are prepared to review pass rate data, provided by PARQ, for CAHSS courses selected by us. PARQ: Data will be provided to Deans early second semester. | STEM: Develop a math certification and tutoring program to address student development and subsequent prerequisite needs in algebra, pre-calculus, and calculus Develop systematic course embedded assessments, which are part of standard practice Further review of student background data, prerequisite performance, and college projections by a college initiated faculty/student research team CAHSS: Final draft of the “plan” to be submitted to Inclusive Excellence committee on May 13, 2011. CEHHS: The course pass rate analysis conducted by PARC staff was reviewed at a CEHHS Council meeting. None of the CEHHS courses that were analyzed indicated a significantly lower pass for underrepresented students. In some courses underrepresented students had a higher pass rate. |
| Inclusive Excellence Plan | Ensure students of color and parents understand the financial aid process and timelines for students to receive appropriate aid. | September 2011 | MSS Director and financial aid Director | MSS staff call, send letter and literature to (MSS) admits and parents to offer support and promote Financial Aid night, College Bowl Sunday, UW Stout Financial Aid and Wisconsin College Access Challenge Grant Resources. MSS staff received training from Financial Aid Director October, 2010. | MSS calls all admits to encourage successful completion of FAFSA and refer students for assistance. Significant collaboration between financial aid and MSS to award Lawton grants (months earlier than last year). MSS meets with each Lawton recipient. Financial aid offered workshop for MSS students. MSS staff does outreach to students with incomplete FAFSA. |
| Inclusive Excellence Plan | Connect students with on campus job opportunities and encourage people to hire diverse student employees. | January 2011 | All Deans and Directors; CAC | CAHSS: Departments have been informed of the Stout Career Link and the efforts of Grad College, Financial Aids, and Career Services. Yhey have been asked to use this service. | Dean of Students: Student Services has employed over 20 students of color during the 2010-2011 year. CEHHS: All program directors have been informed of the Stout Career Link. Underrepresented students are very well represented among our Graduate Assistants. |
| Inclusive Excellence Plan | Increase the number of scholarships and assistantships for diverse student populations. Include inclusive language with the scholarship materials. | May 2015 | Vice Chancellor for Advancement and Marketing |  | No response received. |
| Inclusive Excellence Plan | Teach/inform/educate students on financial literacy. | Plan by May 2011 | SLS- Campus Card Services; TRIO; Financial Aid Director | Campus Card contacted RCU to provide financial information to incoming freshman during summer orientation. This program should be expanded. | No response received. |
| Inclusive Excellence Plan | Explore differential tuition. | BOR proposal in 2/2011 | Chancellor, Provost | After presentation to SSA, decision was made to hold off on proposing differential tuition to the Board of Regents in 2011. | This is still on hold and not being pursued at this time. |
| Inclusive Excellence Plan | Establish faculty exchange opportunities for UW-Stout faculty to teach in other regions of the U.S. or other countries and to invite guest faculty from other areas to UW-Stout. Consider the use of technology to accomplish this. Use the ACE fellows program as a resource. | May 2012 | AVC for EDI; Director of International Education; Deans | Recruitment for AVC for EDI in progress | Provost: AVC for EDI position on hold due to budget |
| Inclusive Excellence Plan | Identify strategies for career flexibility for faculty at various career stages – early career – mid-career – late career. | January 2012 | Women’s Issues group; AVC for EDI | Recruitment for AVC for EDI in progress | Provost: AVC for EDI position on hold due to budget |
| Inclusive Excellence Plan | Develop visibility/recognition program for accomplishments so internal and external audiences can identify campus progress relative to inclusive excellence. | January 2011 | Executive Director of Communications and External Relations | we have a variety of ways (daily e-mail; memos to the campus from the chancellor, provost and others; listening sessions; About Stout; our marketing materials; news releases; etc) to accomplish this “visibility/recognition.” we will continue to use these methods when appropriate and will expand on them when possible. | No response received. |
| Inclusive Excellence Plan | Re-establish women’s issues group | January 2011 | Provost | Committee establishment form is in the process of being updated. | Provost: Women's Issues Group has been assembled and will meet in the fall of 2011. |
| Inclusive Excellence Plan | Expand on accessibility in the classroom to create an inclusive environment for people with disabilities. | May 2015 | ADA Committee; Campus Planner | No update received | ASLS: Campus Planner - All new and reconstructed classrooms must comply with ADA guidelines. This includes major projects, Lab Mod projects and space requests. The ADA and ASA Space Committees are informed of classroom modifications. |
| Inclusive Excellence Plan | Expand national student exchange program. | May 2012 | Director of International Education | No update received | No response received. |
| Inclusive Excellence Plan | Embed Inclusive Excellence in the curriculum through participation in the Compass Institute and other professional development opportunities, including Curriculum Incubation Center and ethnic studies course revision stipends. | January 2011 | Associate Vice Chancellor (ASA) | Nine members were selected for UW-Stout’s Compass Institute team. Eight members of the team participated in this System sponsored Institute November 10-12. The team is assisting ARC with the initial phases of the study to interview recent or soon to be minority students to determine the factors that led to their success. Three Racial and Ethnic Studies courses have been revised by faculty and staff since January 2010. | No response received. |
| Inclusive Excellence Plan | Provide faculty development opportunities related to creating an inclusive curriculum. | Plan by May 2012 | NTLC Director; Faculty Senate (CIC) | NTLC Director will meet with the Faculty Senate CIC Chair next semester to identify and plan a strategy for implementing inclusive curriculum into faculty development opportunities. | NTLC: Met with CIC Chair (Feb. 2011); learned that CIC mainly reviews plans/programs/ courses that are presented to them. They are generally not involved in strategizing their development. NTLC PLAN NTLC is involved in activities designed to infuse Inclusive Excellence across the UW-Stout curriculum. They include: Development of NTLC Sharing Communities (reading group – Fall semester, 2010) and Communities of Practice (2011-12); NTLC sponsored presentations by outside speakers and UW-Stout faculty engaged in diversity-related research and teaching practices (Jan. Professional Development and MayDay 2011-12 events); NTLC collaboration in the design and campus-wide implementation of 2 funded, year-long projects (2011-12): The OPID Undergraduate Teaching and Learning Grant – Infusing Diversity across the Curriculum: A Practical Approach and the Universal Design Summer Institute; NTLC plans to apply lessons learned from funded projects to a larger faculty population starting in summer 2012; Participation in OPID presentation opportunities (President Summit) and other scholarship events. |
| Inclusive Excellence Plan | Conduct UW System Campus Climate Study. | May 2011 | Diversity Leadership Team | Survey scheduled to launch on January 18. | PARQ: Survey was administered. Expect to receive draft report in June, 2011. |
| Inclusive Excellence Plan | Provide training on Inclusive Excellence to supervisors and department chairs. Utilize the “I am inclusive” initiative (goal 6) as an example. | May 2013 | AVC for EDI; Human Resources Director | Recruitment for AVC for ED in progress | Provost: AVC for EDI position on hold due to budget ASLS: HR Director - The HR director position was filled in March 2011. |
| Inclusive Excellence Plan | Incorporate Inclusive Excellence language into employee position descriptions as they become vacant or need to be updated. | May 2015 | Human Resources Director | No update received | ASLS: The HR director position was filled in March 2011. This initiative will be explored in 2011-2012. |
| Inclusive Excellence Plan | Work with every member of the Housing staff to identify at least 3 things they will personally do for our “I AM INCLUSIVE: WE CREATE EXCELLENCE” campaign to further the UW-Stout Inclusive Excellence initiative. | Begin September 2010 | Director of University Housing | Every professional staff member, Desk Services Manager, Resident Advisor, Academic Resource Coordinator, Desk Assistant, Security Assistant, and Graphic Designer has seen the presentation and signed an “Action Sheet.” | ASLS: This was accomplished and we are reviewing the individual goals of the new staff. Not Here Campaign was a multi-office initiative that demonstrated a strong committee to diversity by our university community. |
| Inclusive Excellence Plan | Provide a “Service Learning Day” – which includes working directly with or doing something for people with disabilities, people of color, people from low socioeconomic backgrounds or people living with HIV/AIDS. | 2010-11 | Director of University Housing | Service Learning Day was held on August 30, and 9 Desk Services Managers, 77 Resident Advisors, and 7 Academic Resource Coordinators participated at 6 different sites in the Twin Cities. | ASLS: This was completed and will be institutionalized and an ongoing program. |
| Inclusive Excellence Plan | Maintain inclusive Diversity Leadership Committee to monitor progress. | Sept 2010 | Diversity Leadership Team co-chairs | DLT has been meeting monthly | PARQ: DLT continues to meet monthly |
| Inclusive Excellence Plan | Performance evaluations for senior leaders, including Chancellor Sorensen, need to include Inclusive Excellence. | May 2013 | Faculty Senate; Senate of Academic Staff | No update received | Senate of Academic Staff: The Senate of Academic Staff has made provisions to work with the newly hired Director of Human Resources to address the performance evaluation process for all academic staff, including Senior leadership and the chancellor. This process is schedule to begin late summer/early fall of 2011 and expected to be completed by October 2011. |
| Inclusive Excellence Plan | Require department chairs and unit supervisors to include Inclusive Excellence in department and unit plans and review progress towards the goals in this action plan. Update ESURC template and format. Utilize the “I am inclusive” initiative (goal 6) as an example. | May 2011 | ESURC; Department chairs | No update received | No response received. |
| Inclusive Excellence Plan | Embed Inclusive Excellence questions into course evaluations. | May 2012 | Faculty Senate | No update received | No response received. |
| Inclusive Excellence Plan | Incorporate into university-level strategic planning process – including 6 month updates, gap lists, annual action plan updates, and performance indicators. | Sept 2010 | Director of Budget, Planning and Analysis send out requests; AVC for EDI responsible for providing progress updates and updating the action plan | Inclusive Excellence was included on request for updates in December, 2010 | Provost: AVC for EDI position on hold due to budget PARQ: Updates have been provided as scheduled. |
| Inclusive Excellence Plan | Report regular progress on Inclusive Excellence to System. | As needed | Diversity Leadership Team | We have not received any requests for updates from UW System since initiating our Inclusive Excellence plan | We have not received any requests for updates from UW System since initiating our Inclusive Excellence plan |

39 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | 6 month Progress | Year End Progress |
| Academic Plan | College of Arts, Humanities, and Social Sciences: M.F.A. in Design: Entitlement to Plan approved by UW System Fall 2007. | Authorization to implement: Fall 2010 Implementation: Fall 2011 | Ron Verdon | Planned for approval at February 2011 BOR meeting; implementation now planned for Spring 2012. | Authorization approved by Board of Regents in Feb 2011. Implementation approved for Spring 2012. |
| Academic Plan | College of Arts, Humanities, and Social Sciences: B.F.A. in Graphic Design | Entitlement to plan: Spring 2011 Authorization to implement: Fall 2011 Implementation: Fall 2012 | Ron Verdon & Tamara Brantmeier | In progress as planned. | In progress. Entitlement to Plan has campus approval. System Entitlement to Plan and Authorization in progress. Implementation planned for Fall 2012. |
| Academic Plan | College of Arts, Humanities, and Social Sciences: B.F.A. in Industrial Design | Entitlement to Plan: Spring 2011 Authorization to implement: Fall 2011 Implementation: Fall 2012 | Ron Verdon & Tamara Brantmeier | In progress as planned. | In progress. Entitlement to Plan has campus approval. System Entitlement to Plan and Authorization in progress. Implementation planned for Fall 2012. |
| Academic Plan | College of Arts, Humanities, and Social Sciences: B.F.A. in Interior Design. | Entitlement to Plan: Spring 2011 Authorization to implement: Fall 2011 Implement: Fall 2012 | Ron Verdon & Tamara Brantmeier | In progress as planned. | In progress. Entitlement to Plan has campus approval. System Entitlement to Plan and Authorization in progress. Implementation planned for Fall 2012. |
| Academic Plan | College of Arts, Humanities, and Social Sciences: B.F.A. in Multimedia Design. | Entitlement to Plan: Spring 2011 Authorization to implement: Fall 2011 Implementation: Fall 2012 | Ron Verdon & Tamara Brantmeier | In progress as planned. | In progress. Entitlement to Plan has campus approval. System Entitlement to Plan and Authorization in progress. Implementation planned for Fall 2012. |
| Academic Plan | College of Education, Health, and Human Sciences: BS in Education – Technical Education License 220: Entitlement to Plan in collaboration with UW-Platteville under discussion. |  | Jackie Weissenburger & Sylvia Tiala | Under discussion. | Withdrawn from Academic Plan Spring 2011 due to feasibility concerns. |
| Academic Plan | College of Education, Health, and Human Sciences: B.S. in Health, Wellness and Fitness. | Authorization to implement: Fall 2010 Implement: Fall 2011 | Bob Peters | Authorization to implement passed through the university curriculum process; planned for final approval at the April 2011 BOR meeting; implementation planned for Fall 2011. | Authorization approved by Board of Regents April 2011, implementation Fall 2011. |
| Academic Plan | College of Education, Health, and Human Sciences: M.S. in Gerontology: Entitlement to Plan approved by UW System Fall 2009. Authorization to Implement and Implementation TBD. |  | TBD | On hold. | On hold. |
| Academic Plan | College of Education, Health, and Human Sciences: Ed.D. in Career and Technical Education: Entitlement to plan under discussion. |  | Carol Mooney & Jackie Weissenburger | Under discussion as noted. | Entitlement to Plan under development. Curriculum development was funded through curricular incubation funds for Summer 2011. |
| Academic Plan | College of Education, Health, and Human Sciences: Submajor: Mathematics Education concentration: under development as a concentration of the B.S. in Applied Mathematics and Computer Science. |  | Joy Becker, Chris Bendel, & Jackie Weissenburger | Approved by DPI in fall 2010; courses and program revision in progress to be approved Spring 2011. | Approved by campus in February 2011. Implementation Summer 2011. |
| Academic Plan | College of Education, Health, and Human Sciences: Submajor: Reading Specialist certification: under development. |  | Kimberly Martinez & Jackie Weissenburger | In progress; to be submitted to DPI in January 2011. | Provisional approval by WI DPI May 2011. Full approval anticipated by Fall 2011. |
| Academic Plan | College of Education, Health, and Human Sciences: Submajor: Workplace Diversity minor and professional development certificate: under development. |  | Mitchell Sherman | Passed through the university curriculum process in Fall 2010. | Approved for implementation Summer 2011. |
| Academic Plan | College of Science, Technology, Engineering & Mathematics: Professional Science Master’s (P.S.M.) in Industrial and Applied Mathematics. | Entitlement to Plan: Summer 2010 Authorization to Implement: Spring 2011 Implementation: Fall 2011 | Petre Ghenciu & Alex Basyrov | Entitlement to Plan approved by UW System on September 28, 2010. | In process. Developing Authorization to Implement with final expected end of June 2011. Need to secure approval from Council of Graduate Schools for P.S.M. designation. |
| Academic Plan | College of Science, Technology, Engineering & Mathematics: M.S. in Biomedical Sciences: Entitlement under discussion. |  | Michael Pickart | Under discussion. | Finishing the Entitlement to Plan with anticipated submission in Fall of 2011. |
| Academic Plan | College of Science, Technology, Engineering & Mathematics: Professional Science Master’s: Under discussion in collaboration with Minnesota State Colleges and University System, North Dakota State University, Concordia College, and UW-La Crosse. |  | Jeff Anderson | Received Sloan Foundation grant; Industrial Advisory Board being formed; needs assessment to be conducted. | Feasibility study continuing. |
| Academic Plan | College of Science, Technology, Engineering & Management and College of Education Health & Human Sciences: Food Packaging Professional Development Certification |  | Mary Hopkins Best | Under discussion. | On hold until key faculty are identified who can work on this certification. |
| Academic Plan | College of Science, Technology, Engineering & Mathematics: Submajor: Mathematics Education concentration. Under development as a concentration of the B.S. in Applied Mathematics and Computer Science. |  | Mary Hopkins-Best & Brian McAlister | Approved by DPI in fall 2010; courses and program revision in progress to be approved Spring 2011. | Went through the university curriculum process in Spring 2011. Implementation Summer 2011. |
| Academic Plan | College of Science, Technology, Engineering & Mathematics: Submajor: B.S. Engineering Technology. Investigation of collaborative programming for remote site delivery with UW-Sheboygan, UW-Manitowoc, and Lakeshore Technical College. | Implementation: Fall 2011 | Rich Rothaupt & Scott Springer | Under discussion. | Under development. COBE grant submitted to launch program andnder development. |
| Academic Plan | College of Management: M.S. in Homeland Security. Entitlement to Plan under discussion. | Authorization to Implement: Fall 2011 Implementation: Fall 2012 | Elbert Sorrell | Entitlement in progress through the university curriculum process. | On hold due to feasibility concerns. |
| Academic Plan | Interdisciplinary: M.S. in Sustainability Management: Entitlement to Plan under discussion in collaboration with UW-Extension and other UW institutions. |  | Jackie Weissenburger | Preliminary teleconference has been held. | Two meetings with UW Extension and other UW systems have been held. Authorization to Plan submission to UW System anticipated Fall 2011 with implementation planned for Fall 2012. |
| Academic Plan | Interdisciplinary: B.A.A.S. in Applied Arts and Sciences: Degree completion: in collaboration with UW Colleges (UW-Superior only?) and UW-Barron County. |  | Jackie Weissenburger | In progress. | Entitlement to Plan approved by System. Under development. |
| Academic Plan | Interdisciplinary: M.S. in Innovation and Entrepreneurship: Entitlement to Plan under discussion. |  | Ron Scozzari and Mark Fenton | Will pursue a Certificate in Entrepreneurship first. Proposal for the Certificate has been drafted and will go through the university curriculum process in spring 2011 | Curriculum development for the Certificate has been supported by curricular incubation funds. Curriculum development planned for Summer 2011 with implementation planned for Spring 2012. |

22 action items

| 6 Month Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | 6 Month Progress | Year End Progress |
| AQIP Plan Category 1 | 1P1b – Describe the process for HOW the institution determines the general education objectives: Provide a more thorough description of process to include in the report. | December, 2011 | GE Committee – Kristin Risley | Timeline and responsible parties identified. | Kristin Risley will write a narrative summary of the GE Committee’s process to determine the general education objectives and requirements by September 2011 |
| AQIP Plan Category 1 | 1P4d - Describe the process used for the academic plan of new programs and subprograms as to balancing and integrating learning goals, students’ career needs and realities of employment market; HOW these actions are prioritized and weighted for implementation. | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1P5b – A more clearly defined process of determining discrepancies between required and actual preparation of students: HOW are the requirements determined? | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1P5c – Delineate HOW non-technical transfer and non-traditional students’ preparation are determined. | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1P7b – Identify the policies that guide services provided by the University to help students select programs of study | May, 2012 | Advisement Center, program directors and Provost’s Office – Jackie Weissenburger | Timeline and responsible parties identified. | Jackie Weissenburger will identify all written policies and responsible parties that guide students in the selection of their majors by the end of June 2011 |
| AQIP Plan Category 1 | 1P8b – Underprepared students are identified at a number of points. Establish a process to communicate findings back to the secondary institutions: 1st Year Advisors notify the Registrar’s Office of underprepared students, Registrar’s Office sends letter to the students’ secondary institution. | May 2012 | 1st Year Advisors Registrar’s Office – Jackie Weissenburger with input from Meridith Wentz | Timeline and responsible parties identified. | Jackie Weissenburger will write a narrative summary of the process in which we communicate findings back to the secondary institutions by the end of June 2011 |
| AQIP Plan Category 1 | 1P8c – Identify policies and procedures to engage marginal students prior to academic probation: Offices that work with at risk students identify policies and procedures behind engagement of marginal students and send to the Provost’s Office for inclusion in report. | May 2012 | 1st year Advisors, Counseling Center, TRIO,ASPIRE, MSS and Provost’s Office – Joan Thomas | Timeline and responsible parties identified. | Jackie Weissenburger will ask Joan Thomas to identify all policies and procedures to engage marginal students by September 2011 |
| AQIP Plan Category 1 | 1P12b – Clarify HOW delivery decisions that balance student and institutional needs can be strengthened, particularly when based upon factors other than program need, estimated enrollment and location of students. | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 11P18b – Show the institution’s assessment in a more comprehensive way, integrating the elements of assessment into a comprehensive whole reflecting the interrelatedness among its elements. | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1R1-2,3,5,6 – Develop and present additional metrics that more directly measure student learning; present a more complete picture of student learning: Additional information from Assessment in Major, GE Senior Level Assess., ETS Proficiency Profile, PRAXIS Tests, Fresh. English assessment and Math TLC can be presented. | May, 2012 | Team will gather information from various sources – Jackie Weissenburger & Meridith Went will work with Meridith to develop and present additional | Timeline and responsible parties identified. | Jackie Weissenburger will work with Meridith Wentz and the Writing Center to develop measures of student learning by September 2011. The additional metrics will be presented to the CIC and the Faculty Senate by December 2011. |
| AQIP Plan Category 1 | 1R2b – Differentiate the data used to develop a continuous improvement plan for studying the effectiveness of faculty development. | “O” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1R4e – Employer surveys show a decrease in all competency categories from 2000 to 2006. Investigate to recapture and exceed former performance indicators: Explain the data – may not be statistically significant. | December, 2012 | Committee will work with BPA – Jackie Weissenburger and Meridith Wentz | Timeline and responsible parties identified. | The data and their lack of significance on the employer surveys will be explained in a narrative summary prior to September 2011. |
| AQIP Plan Category 1 | 1R6b - Directly address the comparison of results for student learning outcomes with other organizations: Check to what extent it’s possible to compare – work w/programs & BPA. | May, 2012 | Committee will work with BPA – Jackie Weissenburger and Meridith Wentz | Timeline and responsible parties identified. | A plan will be presented by July 2011 on comparing student outcomes with other organizations. “Other organizations” will be identified by that date. |
| AQIP Plan Category 1 | 1R6c - Compare and measure the faculty’s role in indentifying areas of improvement relative to helping students learn: Will need to seek clarification on the comment to determine how it might be addressed. | “OO” to be included in future plan. |  | To be included in a future plan. |  |
| AQIP Plan Category 1 | 1I1c – Demonstrate cause and effect relationship resulting from specific analyses that lead to specific improvement initiatives. | “O” to be included in future plan. |  | To be included in a future plan. |  |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 2 | 2P4b - UW-Stout has an opportunity to establish the validity of its metrics when assessing the appropriateness and value of its distinctive objectives: Plan is currently being developed by Budget, Planning and Analysis. | 3 Years | BPA, CIO, Research Services, faculty | Charged to PARQ to submit proposal by 12/10 Proposal to be reviewed by CIO, Research Services, faculty(Deans, Senates) CSTEM is in the process of developing a strategic planning process included in that development is the review of data and metrics provided by PARQ for the purpose of understanding the university targets and aligning CSTEM goals to provide positive impacts on these targets. At the same time, the college leadership is reviewing the data, providing feedback to PARQ in cases of results that differ with information available within CSTEM or through other university sources. | In Progress- 5/2/2011 |
| AQIP Plan Category 2 | 2P6b - There is an opportunity for UW-Stout to differentiate both its processes for readjusting distinctive objectives and its processes for establishing new ones: Clarify process for identifying distinct objectives. Determine what is influenced by UW System goals/priorities. | Deferred | Provost, Chancellor |  |  |
| AQIP Plan Category 2 | 2R2b - The institution has an opportunity to establish validity of the instruments used to determine that it is meeting its distinctive objectives. This opportunity exists for instruments that are supplied by vendors as well as for instruments locally developed by the institution: Plan is currently being developed by Budget, Planning and Analysis. | 2 Years | BPA | Charged to PARQ to submit proposal by 12/10 | In Progress- 5/2/2011 |
| AQIP Plan Category 2 | 2R2c- While the institution generally provides conclusions (interprets the data) it has additional opportunities to do so with all of the data presented both positive and negative: A collaboration process needs to be developed to include departments/units in triangulating the data including interpreting the results and impact in relationship to achieving goals and objectives. | 1 Year | BPA, administrative leaders, faculty | A proposal has been written to formalize strategic planning at the college/unit levels. If approved, it will demonstrate alignment between department goals and university goals, as well as in understanding how departments can contribute to achieving the performance indicator targets. Proposal to be reviewed by Deans, Senates, Directors. CSTEM: As updated data and reports become available, these are reviewed by the college chairs groups and brought to department faculty/staff by the chairs. This generates discussion of the underlying assumptions and selections made in data collection and of intended interpretations of the data. Resulting questions or comments are then communicated to the PARQ Director during meetings with the college dean or with college chairs or council. This is significant for aligning CSTEM goals, strategies, planning cycles, and targets with the strategic plans of the university and UW system. | In Progress- 5/2/2011 |
| AQIP Plan Category 2 | 2R3b - Comparison of data to other institutions is included along with internal comparisons. There is opportunity for further comparison with state and national institutions: Efforts continue to identify groups/universities to compare data. Continued challenge but outreach efforts include PolySummit, PolyDasher, UW System, VSA. | 1 Year | BPA | Participation in PolyDASHER continues to expand. We currently have 5 institutions submitting data and 2 more working on submitting data. | In Progress- 5/2/2011 Currently 7 institutions are utilizing the PolyDasher resource. |
| AQIP Plan Category 2 | 2I1a - Improvements to specific programs and activities as well as unit communication vehicles are generated at the unit level. An opportunity exists to compile all of these improvements into an improvement index: Deferred. | Included in an improvement plan in a future year. |  |  |  |
| AQIP Plan Category 2 | 2I2 - In addition to its strategic planning process at the institution – and unit- levels, UW-Stout’s prevailing culture of and infrastructure for, continuous improvement enable it to select processes and set targets to improve performance: Plans need to be developed, reviewed, implemented and evaluated to continually improve the Stout Technological Advantage and Applied Research processes with specific attention to benchmarking with other comparable universities. | 3 Years | BPA, CIO, Research Services, faculty | No progress as of December, 2010. Proposal to be reviewed by CIO, Research Services, faculty(Deans, Senates) Research Services implements the following elements when evaluating the Applied Research Distinct objective: collect and examine from other UW comprehensive campuses and poly peers including number of grants submitted, number in individuals within the proposals (breadth of faculty/staff/student involvement), Number of grants awarded, Number and name of agencies (breadth of funding portfolio), number of IRB protocols submitted, number of IACUC protocols submitted, student research grants, dollars received. These criteria are examined over a three year rolling period for trend analysis by college, department and individual (or equivalent unit to college/department). In addition, the process and results are reviewed with the Provost, Vice Chancellor and the academic deans and dean of students individually for their unit. They provide feedback and insight and direction suggestions. | In Progress- 5/2/2011 LIT is developing an additional template for Strategic Plan. Research Services has developed a draft plan for review. |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year –End Progress |
| AQIP Plan Category 3 | 3P1e- Career services comprehensive report: The information is shared at all levels of the campus but this will be clarified and additional areas of sharing will be included. | 4/15/2011 | Amy Lane-Career services | Career Services collects, compiles and shares information from the annual employment report with the campus community throughout the year. The report is sent to all program directors, Deans and administrators after the January 31 deadline each year. There is a link on Career Services website which is available to all stakeholders of the university. Career Services and Admissions staff shares this report with prospective students for admissions to UW-Stout. Program Directors also use specific information from this comprehensive report to prepare accreditation reports and prepare for site visits. | Career Services distributed an executive summary to the administration, Deans, faculty and staff in February 2011. The comprehensive report is available on the Career Services website for all stakeholders to view. Counselors also highlight this information when meeting with students for individual appointments. This comprehensive report is shared with members of program advisory boards in the spring and fall each year as well as with accreditation teams during site visits. Prospective students and their parents received this information during campus visits and preview days for UW-Stout. A press release was also sent out and printed in the Leader Telegram. |
| AQIP Plan Category 3 | 3P2C-Relationship building with all students including non-traditional and transfer students: Meetings between Student Life Services and Dean of Students to discuss additional collaboration. | 5/1/2011 | Joan Thomas-Phil Lyons-Scott Correll | Survey of transfer student revealed the need to create a separate transfer orientation to meet their diverse needs. The transfer orientation includes components to develop relationships and help the psycho-social needs of non-traditional and transfer students. New processes have been employed to allow transfer students to register in an on-going method to make this more responsive and user friendly. | Residence life provides on-campus housing options for transfer students that are outside of the freshman experience halls. Additionally, the renovated MSC will provide a better support facility for social networking and will include extended hours for dining and studying. The Advisement Center is offering on campus and online orientation/registration options for incoming transfer students in responding to student survey results. |
| AQIP Plan Category 3 | 3P5b-Formal processes to maximize potential future growth and academic needs (ie military veterans): Meetings with Admissions, Student Life and Dean of Students. | 5/15/2011 | Pam Holsinger-Fuchs, Phil Lyons, Joan Thomas | Workforce development data as well as national data on population trends has been utilized to make decisions about future targeted areas of growth. Additionally information from the Equity scorecard was used in identifying the growth of Hispanic/Latino and Southeast Asian students in our primary demographic area. National data as it relates to the increase of veterans in our country influenced a decision to target Veterans. As a result of that a number of initiatives have been employed to provide support for this particular group. | The department of Veterans Affairs (DVA) estimates a 10% increase in enrollment in Higher Education over the next three years in Veteran’s. A veteran’s committee has been established by the Dean of Students office to look at academic needs of veteran students. Collaboration between the OIE, Graduate school and Undergraduate admissions has also occurred relating to International recruitment. Two Memos of Understanding were drafted between Stout and Mpls VA and the Vet Center in LaCrosse to best meet the counseling and transition needs of veteran students. |
| AQIP Plan Category 3 | 3P6C, 3R5d, 3R5c will be addressed year two. 312b, 3R5d, 3R6c will be addressed year three. |  |  |  |  |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 4 | UW-Stout has an opportunity to extend its employee orientation with more personal/relational means like mentoring: A team will be formed to review the research on mentoring systems and make recommendation for Stout including resource needs. | June 30, 2012 | HR Training & Development Coordinator | ASLS will include the development of an effective Classified Mentoring System as a 2011-2012 focused initiative. | Six Month update remains accurate and current. |
| AQIP Plan Category 4 | The University has an opportunity to distinguish separate philosophies and strategies for its training efforts compared to its professional development efforts: A team will be formed to review the literature and develop separate definitions for training and for professional development as well as develop guidelines for distinguishing efforts. | June 30, 2011 | HR Training & Development Coordinator | Separate philosophies will be developed by May 1, 2011. | Separate philosophies were developed and will be forwarded on for appropriate approval. |
| AQIP Plan Category 4 | It is unclear how the personnel evaluation system is aligned with the academic program review process, the educational support unit process, and the training and deployment plan established in 2001. Doing so would show how UW-Stout ensures organizational productivity in the context of institutional goals: Request will be forwarded to the Faculty Senate and Senate of Academic Staff to review and discuss this issue, making recommendation for change, as appropriate. | June 30, 2011 | VC to draft charge for Chancellor. | Charge will be drafted in January 2011. | The senates were charged by the Chancellor to work with the HR director to review the performance evaluation system in 2011-2012 and provide recommendations for improvement. |
| AQIP Plan Category 4 | The institution has an opportunity to interpret and draw conclusions from all the data it presents, both positive and negative: PARQ will establish this guideline as part of their analysis protocols. | January 1, 2011 | Assistant Chancellor of PARQ | PARQ will add a section to our reports after the executive summary that will be a space for interpretations. This section of the report will be included in reports as appropriate | We still plan to include an interpretations section in reports, as appropriate. We haven’t had any such reports since the last update, but anticipate doing this with the ACT Student Opinion Survey. We are also going to pilot a process of having a discussion at a CAC meeting about what to do with the results from this report. If the discussion is successful and meaningful, we will continue such discussions with other reports. |
| AQIP Plan Category 4 | UW-Stout has an opportunity to lead the UW System in validating the metrics used state-wide by the system for comparative purposes: PARQ and others from Stout will volunteer to serve on system-wide committees reflecting on accountability and performance indicators. | Immediately | Various | Charged to PARQ to submit proposal by 12/10 Proposal development is in progress. | This proposal is still in progress. |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Sic Month Progress | Year End Progress |
| AQIP Plan Category 5 | 5P3b: Beyond conducting pre-retreat meetings, a systematic process for collecting and funneling needs and expectations into the strategic planning process is not described Such a process would enable the institution to consider matters that arise prior to, and via other mechanisms, than pre-retreat meetings: Discussions have to take place with the BPA director and others involved in the strategic planning process to better describe the process outlined in the report. | 1/2011 | BPA director and other university officials involved in the strategic planning process. | Met with PARQ director and have received draft of response. Will be completed in 1/2011 as schedule | Completed |
| AQIP Plan Category 5 | 5P5b: There is an opportunity to clarify how being a part of the UW-System affects the decision-making at the institution: Prepare a chart that clearly outlines the decision-making process of the UW System, which includes the comprehensive universities. | 1/2011 | Doug Mell | Narrative begun and will be completed in 1/2011 as schedule | Completed |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 6 | While the University describes a number of measures used for the efficiency and effectiveness of its operations, the various levels of reviewers may find it efficacious to analyze critically the validity of collected data: ASLS Council will ask Budget, Planning & Analysis to provide the scope, effort, and resources to accomplish such a task. We will determine if there are a few key performance indicators for which this exercise should be performed. | March 1, 2011 | VC Assistant Chancellor of PARQ | Charged to PARQ to develop proposal by 12/10. Proposal development is in progress. | This proposal is being combined with the validating metrics proposal from the AQIP Category 4 and is still in progress. |
| AQIP Plan Category 6 | The opportunity exists for UW-Stout to employ Lean Six Sigma tools to reduce waste in transactional processes: A proposal needs to be developed and resources requested to implement this opportunity. University currently utilizes lean to eliminate non-value added steps. Six Sigma will require training and support from a central office. | June 1, 2011 | VC Assistant Chancellor of PARQ | Proposal for funding will be developed by June 1, 2011. | A proposal was developed by Vice Chancellor Moen. The proposal will not be implemented due to budgetary uncertainty. |
| AQIP Plan Category 6 | Data are not provided for performance measures of student and administrative use of technology. This includes technology utilization for instruction and satisfaction with technology support services for students, faculty and administration; effectiveness of the IT Plan and effectiveness of other organization operations: Offices of PARQ and LIT will be asked to meet and review available data for performance measures. If data is not available, a proposal to develop will be requested. | June 1, 2011 | CIO Assistant Chancellor of PARQ | A meeting will be scheduled to review available data for performance measures. | A paragraph will be added to category 6 – Supporting Organizational Operations that the performance measures for student and administrative use of technology are available in category 7 and the Satisfaction with Learning and Information Technology survey will be conducted on a regular basis – every five years. |
| AQIP Plan Category 6 | There is an opportunity for the institution to exceed national/industry averages on a more consistent basis for student life services: ASLS will utilize key national/industry averages as division performance indicators. SLS units will also regularly track, analyze and discuss survey results. | Ongoing | VC AVC SLS | The ASLS division has established performance indicators that include national/industry benchmarks. The performance indicators are reviewed on a biannual basis and opportunities for improvements are discussed. Focused initiatives are identified and implemented based on the data as appropriate. | 6 month update remains accurate and current. |
| AQIP Plan Category 6 | There is an opportunity for the institution to exceed national and industry averages on a more consistent basis for physical plant and health and safety performances: ASLS will utilize key national/industry averages as division performance indicators. Physical Plant and Health & Safety units will also regularly track, analyze and discuss survey results. | Ongoing | VC PP Director ED Health & Safety | The ASLS division has established performance indicators that include national/industry benchmarks. The performance indicators are reviewed on a biannual basis and opportunities for improvements are discussed. Focused initiatives are identified and implemented based on the data as appropriate. | 6 month update remains accurate and current. |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 7 | While UW-Stout states that is has systematic processes and identifies responsible parties, the institution has an opportunity to clearly define how it selects, manages, and distributes data and performance information that support its programs and services: Review and enhance existing documentation for the planning process to ensure it adequately addresses how data and performance information are selected, managed and distributed. |  | BPA director | No progress as of 12/17/2010 | No progress. |
| AQIP Plan Category 7 | Results data for key indicators and their targets could be provided in a matrix that aggregates information (bi-) annually, providing an overview of organizational strength and continuous improvement as well as identifying potential action projects: Modify figure 8-4 in the AQIP portfolio to address reviewer concerns. |  | BPA director | No progress as of 12/17/2010 | No progress. |
| AQIP Plan Category 7 | In light of its collection and evaluation of comparative data, there may be an opportunity for UW-Stout to determine the relevance or validity of these metrics with a view to establishing causality: Conduct a validity study to identify which metrics are related statistically to the performance indicators. Use this information to make changes to the metrics reported on in AQIP. | Proposal by 10/10 Obtain approval and implement starting 1/11 | ARC | Charged to PARQ to develop a proposal by 12/10 | Proposal is still in progress. |
| AQIP Plan Category 7 | UW-Stout has elements in place to ensure the integrity of its information systems and processes and may have a greater opportunity to develop an overarching approach to ensure its integrity: Develop and document an overarching approach to ensure data integrity. |  | LIT | We are proposing a change to this action item to say: A two-pronged approach is proposed: 1) to develop a list of guidelines and safe practices. One tool that will be used in develop this list is a listing of all the external requirements related to integrity. 2) work with impacted offices on campus to implement the guidelines Implement comprehensive security policy. LIT will be responsible for developing a proposal for phase 1 by June 30, 2011 | LIT: proposal for phase I is in progress. |
| AQIP Plan Category 7 | While UW-Stout is recognized as a leader in performance measurement both in and beyond the University of Wisconsin System, there is an opportunity to present supporting documentation of awards, performance leadership and peer recognition: Identify awards to pursue related to our performance measurement system and submit at least one award application per year. |  |  | No progress as of 12/17/2010 | PARQ: Award application was submitted for PolyDASHER. |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 8 | We propose to combine these: -UW-Stout the opportunity to further define its benchmarking processes and processes by which it sets its targets -The University has an opportunity to identify and demonstrate how specific targets are the result of, or are linked to the analysis of specific data, thereby clearly establishing drivers for target-setting: Use PolyDASHER as a tool for this – but wait another year until it is more fully established to implement. | - | BPA director | 5 institutions currently submitting data to PolyDASHER; 2 more institutions in discussion phase. | 7 institutions are currently participating in PolyDASHER |
| AQIP Plan Category 8 | We propose combining all of these together: -The University has the opportunity to further define the process it uses to provide and validate information and data to establish performance indicators -There is an opportunity for UW-Stout to develop a process for establishing the validity of the metrics it employs. By establishing metric validity, the University will be able to determine causality with greater accuracy which will enable it to pursue more effective improvements. -The University has an opportunity to validate metrics with a view to establishing causality: Conduct a validity study to identify which metrics are related statistically to the performance indicators. Use this information to make changes to the metrics reported on in AQIP. | Proposal by 10/10 Obtain approval and implement starting 1/11 | ARC | Charged to PARQ to develop proposal by 12/10 | Proposal is still in progress. |
| AQIP Plan Category 8 | It is not clear how “gaps” identified in risk analysis, which is conducted every 5 years, are incorporated into the annual Strategic Planning Process: Formal memo to the action plan leaders on an annual basis, with a list of gaps related to their action plan, requesting a response to the Chancellor – either resolution, or requesting that it be dropped | June 30, 2010 | Director BPA | This memo will be sent out after the year-end action plan progress SPG meeting in May. | This memo will be sent out after the year-end action plan progress SPG meeting in May. |
| AQIP Plan Category 8 | We propose to combine these: -The University has an opportunity to specifically discuss the areas in which it has not achieved its targets -While its overall institutional performance is equal to or better than its benchmarking groups, there is an opportunity for UW-Stout to improve by addressing/discussing areas in which comparisons are less favorable: Negative data trends are addressed through the AQIP process improvement plan. | September 13, 2010 | AQIP process improvement action plan leaders | This is addressed via the new AQIP process improvement action plan. Action plan leaders are responsible to identify how we will respond to all of the AQIP concerns. | This is addressed via the new AQIP process improvement action plan. Action plan leaders are responsible to identify how we will respond to all of the AQIP concerns. |
| AQIP Plan Category 8 | UW-Stout should expand goal benchmarking outside of the UW System and on a national basis: Utilize PolyDASHER to accomplish this. | June 30, 2010 | BPA director | 5 institutions currently submitting data to PolyDASHER; 2 more institutions in discussion phase. | 7 institutions are currently participating in PolyDASHER |
| AQIP Plan Category 8 | The culture and infrastructure at UW-Stout affords this institution the opportunity to go beyond its present approach and pursue a Six-Sigma or equivalent approach to continuous improvement: Evaluate feasibility of pursuing Six Sigma. | - | Chancellor | No progress as of 12/17/2010 | Proposal submitted but is not being pursued at this time due to budget constraints. |

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| AQIP Plan Category 9 | The institution has an opportunity to develop a more comprehensive and systematic approach to collecting and analyzing feedback data from its collaborators. Satisfaction levels of collaborators should be included: Request that all units that work with external collaborators identify at least one method of collecting and analyzing feedback. | June 30, 2011 | Executive Director of Enrollment Services Executive Director of the Discovery Center Director of International Education Dean of Students | Charge will be given to responsible individuals in spring of 2011 | Charge given to responsible individuals in May 2011 |
| AQIP Plan Category 9 | There are no clear references to the processes used to set and improve targets relative to collaborative relationships: Request that all units that work with external collaborators set appropriate targets. | June 30, 2011 | Executive Director of Enrollment Services Executive Director of the Discovery Center Director of International Education Dean of Students | Charge will be given to responsible individuals in spring of 2011 | Charges given to responsible individuals in May 2011 |

36 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| Marketing Plan | Creation of the Integrated Marketing Team: Marketing staff has developed the framework for an integrated marketing team to assist in coordinating university-wide marketing efforts. | Fall 2010 and ongoing | Director of Integrated Marketing Staff | Currently working on the creation of a centralized marketing unit on campus to serve the needs of the campus. This unit is projected to start 7/1/2011. | The integrated marketing staff and team will be implementing a new online request system in July, 2011. |
| Marketing Plan | Implementation of revised identity standards program: IM staff will introduce the revised identity standards program to the campus through presentations, UW-Stout Today, an identity website and an e-mail from the administration highlighting the new program. | September 2010 and ongoing | Director of Integrated Marketing, Web Coordinator, University Editor and Printing Services Assistant | Revised Identity program was implemented in September 2010. Marketing/Communications staff presented revised identity standards to entities, colleges and councils across campus. The identity website was also revised and can be found at www.uwstout.edu/identity | The Revised Identity program is up and running on campus. Strategy completed. |
| Marketing Plan | Incorporate Inspiring Innovation theme into marketing materials: All authors of marketing materials will incorporate the Inspiring Innovation message into marketing materials it creates. | Summer 2010 and ongoing | Integrated Marketing and Communications staff | The Inspiring Innovation marketing theme has been incorporated in marketing materials, billboards and banners on campus. | The Inspiring Innovation marketing theme has been incorporated in marketing materials, billboards and banners on campus. |
| Marketing Plan | Photography: Inspiring and current still photography is crucial for effect presentations on the website and in publications, and for other media. Hire a photographer throughout the 2010-2011 academic year to take photos for various marketing uses. Place photos in strategic locations around campus. | Fall 2010 and ongoing | Integrated Marketing and Communications staff | Bill Wikrent, Don Steffen and Jill Olsen have taken photos of events on campus this past fall and we have hired a photographer to take class photos this February/March. | Staff and hired photographers have taken photos on campus throughout the year and will continue to take photos to populate the website and marketing materials. |
| Marketing Plan | Ask Faculty and Staff for Success Stories/Students and Alumni to highlight in advertising campaigns: While the Communications and Marketing staff present the marketing process to faculty and staff at workshops, staff will hand out a request for faculty and staff to identify individuals – students, alumni, faculty, staff should be highlighted by the university in marketing campaigns, news story ideas, the Stout Outlook alumni publication, the StoutQuest research publication and more. | September 2010 and ongoing | Integrated Marketing and Communications staff | Marketing and Communications staff have presented to the colleges, councils and entities on campus requested success story ideas that can be used in the E-Outlook, for press releases and in marketing materials. | Success stories are an integral part of communications and marketing on campus – highlighted in press releases, marketing materials and will continue to be a strategy in upcoming marketing plans. |
| Marketing Plan | Continue to work on website redesign project for the university: Work with selected website design vendor to implement website redesign project and intranet development project on behalf of the university. | May 2010 and ongoing throughout 2010-11 academic year | Website project team: Maureen Carlson, Doug Wahl, Kay Schnur, Dave Williams, Doug Mell, Pam Holsinger-Fuchs, Ron Verdon, Amy Lane and Phil Lyons | The website redesign project is underway. We have completed the listening sessions in the fall of 2010 and have taken the feedback from the listening sessions to develop the suggested navigation and template for the home page. The Senior Administration has approved the look of the home page and we are currently finalizing the navigation. | The website redesign project is in full swing. We are finalizing the prototypes and will be supplying content for migration to Fig Leaf over the summer. |
| Marketing Plan | Continue to replace banners for the campus to illustrate the Inspiring Innovation theme and create photo marketing opportunities on campus: Continue with a series of outdoor, four-season light post banners to be placed on campus to further promote the polytechnic designation through the use of the Inspiring Innovation theme. | Fall 2010 | Integrated Marketing staff | The banners on campus were replaced Fall of 2010. We will continue to add banners to the North campus in the 2011-2012 academic year. | Banners have been replaced as needed and banners have been purchased for the north campus. The new banners will be up in April/May, 2011. |
| Marketing Plan | Laptop communications: Use the university laptops and network as tools to promote the marketing theme. Create a new wallpaper screen on university laptops using the Wisconsin’s Polytechnic University tagline. This will be the first screen that pops up when the university laptops boot up. The University Marketing Team will continue to investigate ways to incorporate the Wisconsin’s Polytechnic University and the Inspiring Innovation marketing themes through the laptop program at UW-Stout. Additionally, investigate developing a laptop skin for the outside of the laptops. | Summer 2010 for wallpaper change and ongoing throughout 2010-2011 school year for investigating potential marketing opportunities through the laptop program | Integrated Marketing staff | A new wallpaper was created and submitted to LTS staff and added to all laptops for the 2010-11 academic year. | Strategy completed. |
| Marketing Plan | Develop two minute program videos to highlight each undergraduate program: Develop videos to promote each undergraduate program to be used on program websites and possibly in additional marketing avenues such as web banner ads, mall kiosk advertising, in presentations and to play on closed circuit TV’s on campus. | May, 2010 and ongoing throughout 2010-11 academic year | Integrated Marketing and Admissions staff | Currently working on the development of program videos for the undergraduate programs at UW-Stout. Three videos have been completed and 12 more are currently in various phases of production. We will continue to work on the development of videos for the remaining programs during the winter/spring 2011. It is likely that we will continuing work on the videos during the 2011-12 academic year. | 15 program videos completed and 10 more are currently under development. |
| Marketing Plan | Advertise on Zinch: Continue partnership agreement with Zinch (an online site for prospective students and international students). | Ongoing throughout 2010-11 | Admissions staff | We continue to advertise with Zinch. | Strategy completed. Will continue to advertise with Zinch. |
| Marketing Plan | Web Banner Advertising: Advertise to prospective traditional, non-traditional and distance education students on various websites including: Get Educated, Wisconsin Public Radio, Minnesota Public Radio and others to promote the variety of academic options available to all students at UW-Stout. | Summer 2010 and ongoing | Integrated Marketing staff | We are currently advertising on MPR, WPR and WEAU.com. Marketing staff is currently investigating Get Educated.com and the possibility of collaborating with other UW-System schools that do not have competing online programs. | Strategy completed. Will continue banner advertising in 2010-11. |
| Marketing Plan | Explore viral marketing and Mall Kiosk advertising opportunities: Promote the distance education and traditional education options at UW-Stout. | 2010-2011 academic year | Integrated Marketing staff | Currently advertising at the Mall of America – running TV commercials and have a mall kiosk ad at the Oakwood Mall. | Strategy completed. |
| Marketing Plan | Specialty Magazine Advertising: Advertise in Minnesota Monthly magazine. Minnesota Monthly is the region’s most widely circulated lifestyle magazine, catering to a well-educated, affluent audience. Key topics—mainly with a strong focus on Minnesota—include politics, education and healthcare. Minnesota Monthly is also a popular resource for local entertainment, travel, arts and dining opportunities. The magazine has a subscription base of 65,000 with 75% of the readers being aged 35 and older. Advertise in the following issue in 2010: September 2010. | Produce ads in July/August | Integrated Marketing Staff | Advertised in the September 2010 issue of Minnesota Monthly the Back to School issue. The Marketing team has decided not to advertise in this publication moving forward and to use the funds for other marketing strategies. | Strategy completed. |
| Marketing Plan | Billboard Advertising: UW-Stout will advertise on two billboards to build the image of being Wisconsin’s Polytechnic University and to promote the Inspiring Innovation theme. | May/June 2010 renewals | Integrated Marketing staff | Currently we have four billboards – one we have not renewed, but our advertisement is on this billboard. The billboards all reflect our inspiring innovation theme. | Strategy completed. |
| Marketing Plan | Continue institutional presence on Facebook and Twitter: Promote links whenever possible and purchase banner ads whenever possible. | Ongoing | University Communications | The Communications and Admissions office are actively involved with Facebook and Twitter. | The Communications and Admissions office are actively involved with Facebook and Twitter. |
| Marketing Plan | Advertise in High School Student Planners: Continue to advertise in targeted high school student planners promoting the variety of educational options at UW-Stout. | Fall 2010 and ongoing | Integrated Marketing and Admissions staff | We are continuing to advertise in targeted high school planners. | Strategy completed. |
| M Marketing Plan | Reserve funds for printing and special marketing initiatives for 2010-2011 academic year. | Ongoing | Integrated Marketing | The reserve funds have been used for additional marketing expenditures including – retractable banners that were used for the Jarvis Hall Grand Opening – these banners can be used for any special events, printing of marketing materials and more. | Strategy completed. |
| Ma Marketing Plan | TV advertising | 2010-2011 | Integrated Marketing | Run TV commercials from November through February 2011 to the target audiences of teens, 18-24, Non-traditional students and parents in Western Wisconsin and the Twin Cities. TV ads are running on programs high appeal including: Saturday Night Live, the High School Sports Wrap, ESPN, WEAU news, Dirty Jobs, Glee, Gossip Girl, 2 ½ Men, the Late Show and Letterman. | Strategy completed. |
| A Addition to the Marketing Plan | Video development for targeted populations | 2010-2011 | Admissions and Integrated Marketing | Through the Inclusive Excellence plan – the Admissions and Integrated Marketing staff have been asked to develop videos to reach out the Hmong, Hispanic, Native American, African American, LGBTQ, and non-traditional populations. This project is starting in January 2011 and most likely will continue into the 2011-12 academic year. | Videos are currently under production and should be completed in May or June, 2011. |

19 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| UP- Diversity | Conduct an in depth qualitative study that involves a series of interviews with students of color to assess how to improve graduation rates for minority students at UW-Stout. A series of recommendations based on the study would be shared with the campus. | May 2011 | Meridith Wentz/ARC (primary), Pam Holsinger-Fuchs and interested Social Science faculty, see note below, MSS Office | Part of this project was assigned to the Compass institute participants. The Compass institute participants are currently recruiting for racial/ethnic minority graduate students to serve as facilitators. | PARQ: Data collection has been completed. Analysis is in progress. Report will be provided in September |
| UP-Diversity | Conduct quantitative market research in order to generalize the results from the qualitative study to the UW-Stout population | May 2012 | Maureen Carlson (primary) and ARC | Will not be starting until after the qualitative study is done. | Will not be starting until after the qualitative study is done. |
| UP- Enrollment Management | Investigate the providing of user friendly methods of payment for tuition and fees that are more convenient than currently offered options; consider on-line delivery options. Provide a summary report to the Chancellor. | June 30, 2011 | Registration and Records, Student Business Office (primary), Information Technology, Student Service Units including Housing. | New payment methods are being implemented via Touchnet. Should be ready in Spring Rick Olson will be working with this group to look at issues. Credentials Solutions (TranscriptsPlus) will add credit card option to students ordering transcripts. | ASLS: New options have been explored. Options include a newly implemented payment system that gives 3rd party payment/account access controlled by students, and will give additional payment options for students including a new Secure Vault Payment method, VISA acceptance for CI students and dorm deposit payments online by the end of June. Peer Transfer is being investigated to allow easier and less expensive payment for international students from any country. Enrollment services: Registration and Records now uses Transcripts Plus software allowing for all credit cards as well as debit card payment for transcripts. |
| UP- Enrollment Management | Investigate the elimination of the paper add/drop card. Provide a summary report to the Chancellor. | December 31, 2010 | Registration and Records, Faculty Senate/EAC (primary). | This similar issue (see below) was passed unanimously by the EAC and the Faculty Senate Exec Board. Full Senate vote schedule for 12/14/10. Faculty will still have final word for course overload (full class) and dropping of course after 10th day. | Enrollment services: Paper program cards will be greatly reduced by new drop/add policy approved by faculty senate. Students in regular term courses will add online for 5 days and drop online for 10 days. Students in quarter courses will drop online for the first 5 days of the quarter. Students in irregular scheduled courses can add/drop up until the start date of the course regardless of start date. |
| UP- Enrollment Management | Investigate allowing students to add/drop classes up to the first day of class and then during the first few days of class. Provide a summary report to the Chancellor. | December 31, 2010 | Registration and Records, Faculty Senate/EAC (primary). | This was passed unanimously by the EAC and the Faculty Senate Exec Board. Full Senate vote schedule for 12/14/10. Faculty will still have final word for course overload (full class) and dropping of course after 10th day. | Enrollment services: Paper program cards will be greatly reduced by new drop/add policy approved by faculty senate. Students in regular term courses will add online for 5 days and drop online for 10 days. Students in quarter courses will drop online for the first 5 days of the quarter. Students in irregular scheduled courses can add/drop up until the start date of the course regardless of start date. |
| UP- Enrollment Management | Investigate the use of online waitlists. Provide a summary report to the Chancellor. | December 31, 2010 | Registration and Records, Faculty Senate/EAC (primary). | This is being considered. Feasibility to ensure fairness to students is being examined. | Enrollment services: This functionality is available in PS; however, the feasibility of implementing it does not necessarily ensure fairness to all students as students are added to the course based on who can take it (schedule opening, credit hour opening) not in first-come, first-serve manner. |
| UP- Enrollment Management | Investigate the possibility of informing students of important dates regarding refunds and withdrawals important dates. Provide a summary report to the Chancellor. | June 30, 2011 | Registration and Records, Information Technology, Faculty Senate/EAC (primary), Business Office | Students are sent emails from Bursar for all payment date reminders. Also have dates on Bursar website and Facebook page A link was added to DE student letters. Information was included in Daily email to students. Message was added to R & R website. R & R website updated weekly with important dates. | ASLS: Business Office – six month update remains current and accurate. |
| UP- Enrollment Management | Investigate a system in which each individual course has its own individual schedule which allows for add/drops outside of the traditional academic calendar. (Review BOR policies) Provide a summary report to the Chancellor. | June 30, 2011 | University Registrar, Faculty Senate/Educational Activities Committee (primary); Business office; Financial Aid office | Bursars has been involved in this only as they would have to set up payment calendar in software Using dynamic dating currently. Investigating feasibility of PS functionality to allow drop/out outside the traditional semester schedule. | Enrollment services: For students who have irregular scheduled courses (does not conform to standard term calendar), PS/AccessStout now allows drop/add of course online up until the start date of the course. |
| UP- Enrollment Management | Investigate joining the “Return to Wisconsin” consortium/group – a System initiative whereby children of alums are given in-state tuition to participating institutions. Stout should join the consortium. This requires BOR approval (differential tuition). Provide a summary report to the Chancellor. | June 30, 2011 | Admission and Enrollment Services (primary). Foundation office | There is not currently a "consortium" that has to be joined. A number of the WI colleges offer this program but there is not a formal consortium. Wording of this action item should be changed. Information has been gathered and will be presented to the Chancellors Cabinet. | No response received. |
| UP- Enrollment Management | Investigate scholarship application process to be streamlined allowing for the submission of materials on-line and eliminating the paper copies for reviewers. Reviewers would be requested to access materials electronically. Provide a summary report to the Chancellor. | June 30, 2011 | Alumni Foundation, Information Technology, Enrollment Management and Admissions, University Community and Alumni Reviewers, Dave Williams (primary) | The foundation has created an on-line scholarship application process using a company named WizeHive. The on-line application is set to go with the scholarship deadline of January 28th, 2011. | No response received. |
| UP- Enrollment Management | Automation of distribution of transcripts (online service) | September 2010 | Enrollment Services | Credentials Solutions will provide this service. Working with IS to get the software installed and the goal is to have this operational in early to mid January. | Enrollment services: RoboRegistrar, a service of TranscriptsPlus went live on 2/15/2011. Transcript ordering can now be done online with credit and/or debit cards and include a FedEx expedited delivery options. Transcript orders leave R/R within one day of order, unless transcript needs verification (2 day max). |
| UP- Experiential Learning | Develop a standardized definition and proposal for the implementation of extra-curricular and co-curricular activities in a transcript or portfolio. | January 2011 | Implementation team, led by Mary Hopkins-Best and Phil Lyons, team also includes students | Charge went out to implementation team from Chancellor in August. In Progress- Committee is meeting following listening sessions we have held meetings in November (11/15) and December (12/6 and 12/13) – work is progressing. Will be completed near the end of January. | ASLS: Report (1/26/11) was sent and accepted by the Chancellor. Definitions for extra-curricular and co-curricular activities were developed for inclusion in a transcript housed in Org Sync Portal. CEHHS: Completed in December |
| UP- Experiential Learning | Designate an individual to be responsible for the coordination of service learning and civic engagement (reassignment). | January 2011 | Phil Lyons, Assistant Vice Chancellor, Student Life Services | Completed – Jeremy Gragert will be responsible; he started his duties on December 6th. | ASLS: A service learning and civic engagement position (one year appointment) was created and filled. The position will be evaluated during the summer and following the hire of a permanent MSC Director. |
| UP- Experiential Learning | Develop a campus-wide steering group to assist with the coordination of service learning and civic engagement activities. | May 2011 | Service Learning & Civic Engagement Coordinator (to be named) | Jeremy is aware of this priority and we have a concept with members developed for a consideration by stakeholders. | ASLS: It was determined that two groups be created to coordinate; one for service learning consisting of a Dean’s representative from each College and an group to guide community service and civic engagement. |
| UP- Experiential Learning | Investigate the use of Org Sync or another tool to track and report service learning and civic engagement activities and develop a proposal for the Chancellor to approve. | January 2012 | Service Learning & Civic Engagement Coordinator (to be named) | This topic has become central to the discussions that are occurring in the co-curricular transcript group. The proposal will likely be developed out of the findings of that group. | ASLS: This is on-going, the grant project will conclude in July of 2011 and an informed proposal and presentation will be created for the Chancellor. Completion of project still estimated to be in January of 2012. |
| UP- Experiential Learning | Review and update the membership and charge of the existing Learning Community Advisory Committee. | November 2010 | Joan Thomas, Dean of Students | Charge went out to Dean of Students from Chancellor in August Completed in September 2010. | Completed |
| UP- Experiential Learning | Continue to research best practices related to learning communities and develop a proposal to the Chancellor for how to continue to implement learning communities at UW-Stout. | May 2011 | Learning Community Advisory Committee led by Joan Thomas, Dean of Students | In progress. Learning Community Coordinator attended the National Learning Community Conference in November. Highlights will be shared during Professional Development Week. | Dean of Students: Proposal completed |
| UP- Experiential Learning | Research and development of a model to achieve 2015 targets for numbers of learning communities and numbers of students enrolled in learning communities. | February 2011 | ARC/BPA | In progress. | PARQ: Project cancelled because number of learning communities proposed for 2011 was already enough to meet 2015 targets |
| UP- Experiential Learning | Determine the comprehensive costs/resources associated with current learning communities; project costs/resources associated with adding additional learning communities and develop a proposal for the Chancellor for any funding needs for 2011-12. | May 2011 | Joan Thomas, Dean of Students | In progress. 25 learning communities have been proposed for 2011 which is double the number proposed for 2010. Once proposed learning communities are confirmed and a proposal is developed a budget for 2011-12 will be submitted. | Dean of Students: Budget developed |
| UP- Experiential Learning | Implement the plan to achieve the 2015 targets for learning communities. | Fall 2011 | Learning Community Advisory Committee led by Joan Thomas, Dean of Students | With 25 proposals for 2011, we are on track to meet and exceed the 2015 targets. |  |

20 action items

| Year End Progress Update |
| --- |
| Name of Action Plan | Task | Due Date | Responsible | Six Month Progress | Year End Progress |
| IT Plan | Secure Wireless: Wireless technology has historically not been secure. New technology has enabled dynamic encryption providing Stout a means of secure wireless communications. | Fall 2010 | T&N | Technology available now. Communication to the campus being developed. In progress. Information to be provided to campus second semester via daily email and LIT newsletter. | Complete |
| IT Plan | Residence Hall Wireless: Wireless connectivity is available in all study and common areas within the residence halls. Student have requested to have wireless connectivity in their rooms to help facilitate group study, etc. | Fall 2012 | Residence Life, T&N | Hansen and Hovlid Halls are current pilots. CKTO and HKMC scheduled for 2011. | In progress. |
| IT Plan | Web Server Content Management System: CommonSpot provides a centralized, supportable system for campus web authors to update and maintain the content of their websites. | Fall 2010 | EIS, Marketing | Conversion to CommonSpot complete. Version 6 of CommonSpot will be implemented along with the new hardware to support the new redesigned website and CommonSpot infrastructure. Developing requirements with ReDesign Committee and Fig Leaf. Reviewing outcomes from listening sessions. Decided to move forward with EMS Master Caldenaring as a campus wide calendaring application that would be integrated into the website. Initial designs have been submitted by fig leaf and are being evaluated. | Complete |
| IT Plan | Web Redesign: One of the recommendations of the web audit was to consider a web redesign for Stout’s marketing focus and separating internal and external audiences. | Spring 2011 | EIS, Marketing | RFP awarded to Fig Leaf Inc. Project is underway with listening sessions being conducted Fall 2010. Listening sessions completed. Initial designs submitted to Stout by Fig Leaf and in the process of evaluation. | Home page and secondary pages prototyped and shared with campus. Go live including conversion slated for August 2011. |
| IT Plan | Faculty/staff Email System Replacement: Stout's email system was purchased 5 years ago. The hardware is out of warranty and in need of replacement. There is also a need to increase mailbox size for faculty and staff. | Fall 2010 | T&N | In progress. Complete. | Complete |
| IT Plan | Information Portal: Design, build and implement an information/report portal that consolidates all university data to a single location accessible from the UW-Stout web site. | Fall 2010 | BPA, T&N | Consultants from Omni Resources Inc. providing framework with Sharepoint. In design phase. Design phase complete with data being populated in the system. | Development complete. System now being populated with files. Anticipated launch date Fall 2011. |
| IT Plan | Professional Development Tracking System: Stout is currently investigating a partnership and/or outsourcing with UW-Madison's Office of Human Development relating to a professional development/training tracking and registration system. | Spring 2011 | HR, LIT | Contact with Madison and awaiting IAM implementation prior to deployment of the system. Awaiting completion of DoIT staff for integration with IAM for access using campus credentials. | As of 5/25/2011 authentication for UW campuses complete. Next steps to be defined and executed. |
| IT Plan | Build a Financial Aid portal: Automate and simplify the process of applying for and receiving financial aid. Make FA and AR information and processes available to students and staff (FA Counselors). | Spring 2011 | EIS, FA | Financial Aid Office is very much interested in pursuing a portal for the services provided by their office. Concept can be investigated following PeopleSoft implementation. Future feature packs for PeopleSoft to have this capability. No progress as of 12/2010. | No progress as of 5/2/2011. |
| IT Plan | PeopleSoft HR System: UW System is starting the project to convert the current HR system to PeopleSoft HR. This project is to replace the previously unsuccessful implementation of the Lawson system (APBS). | Spring 2011 | EIS, HR | Performing fit-gap sessions to determine what is needed for campus end users that may not be in place in HRS. Tentative completion fall 2010 with a deliverable of gaps that need to be addressed. Reporting group is reviewing delivered reports and EPM data warehouse solution. Data conversion tasks are being preformed. Reviewing shadow and supplemental HR systems on campus and how they will be addressed with HRS or not. IAM person hub integration is being deployed and tested. HRS go live tentative for second quarter 2011. Progress relatively on time with go live April – May 2011. | Go live April 18, 2011 on time. Working through various issues. |
| IT Plan | Reporting Data Store (RDS) - data warehouse: UW-System owns the RDS software that was originally developed by PeopleSoft. Multiple campuses in the UW-System have implemented this software. With the PeopleSoft Campus Solutions implementation a solution is needed for the current data warehousing environment that was developed with Datatel student information. | Spring 2011 | Admissions, BPA, EIS, FA, R&R, SBS | All modules are live with data from production PeopleSoft. Data dictionaries developed for all modules with updates being made as needed. Campus User group formed to address gaps in knowledge for campus query writers. Plans to load transfer credit data to RDS. Meetings scheduled 2-3/semester to resolve any issues. Campus end users to be trained Summer 2011. | Training scheduled for data leads. End user training slated for summer 2011. |
| IT Plan | Oracle EPM 11.1.1.2 upgrade: The University of Wisconsin – System is upgrading/migrating from Hyperion 8.5 Interactive Reporting to Oracle EPM 11.1.1.2 (sometimes referred to as Hyperion 9.5). The current version is unsupported by the manufacturer. | Spring 2011 | EIS, UW System | Upgrade planned for after January 2011. Published query users will first be transitioned then will convert to new version. Will transition client-based users to web-based tool. Postponed until Spring 2011. | Slated for completion by August 1, 2011. |
| IT Plan | Reporting Software: University of Wisconsin-Stout is looking for an advanced yet intuitive solution to solve the varied reporting needs of the Business and Financial Services Department that are not being met currently in the multiple reporting tools available. | Fall 2010 | EIS, SBS | RFP awarded to eThority. Data verification underway. Software installed on server with training conducted. | Financials in final testing. Looking to expand with HR and Student Financials data. |
| IT Plan | Implement Additional Network Security: Continue to enhance UW-Stout security practices to protect against viruses, worms and spam e-mail via the use of software and hardware appliances. Also conduct external annual security audits to help protect Stout's data systems. | Ongoing | T&N | External security audit in progress. Complete. Currently implementing recommendations from security audit. Annual external audits will be performed. | Complete |
| IT Plan | Comprehensive Security Policy: UW System has recommended that a Comprehensive Security Policy be developed for campuses that don’t have one. | Fall 2011 | LIT | Development begun. In progress. Many security changes will result as HRS system implemented. | In progress |
| IT Plan | Update digital image databases and put historical images online: The university has over 250,000 photographs (1890 through today) and we’re adding thousands of new ones each year. The photos have significant value to the campus and are used by departments, organizations and individuals. Some are digital and accessible but many are not so we’re scanning old negatives, adding images, and upgrading the database to make it more useful while ensuring compliance with network changes and security. | Spring 2011 | LTS, T&N | Software purchased and installed. Migration of photos started with implementation and training of use for departments in need to follow. Complete. Use training initiated. | Complete |
| IT Plan | ASK5000 help desk facility: The current facility is not efficient nor optimally located for student access. Space within Millennium Hall will be evaluated for consolidating repair, inventory/deployment and the ASK5000 helpdesk. | Spring 2011 | LIT | Currently evaluating location of LTS, NTLC and T&N staff to provide better service to students and faculty for the help desk and NTLC. Store front, cubicles and work stations ordered for move in March 2011 to former Nakatani lab area. | Complete |
| IT Plan | Classroom Equipment Maintenance Schedule: Develop schedule for regular maintenance, replacements and upgrades for software and hardware supported by LIT. | Fall 2010 | LTS | Initial schedule completed. Reviewing integration with the EMS campus scheduling software. Integrating data into EMS campus scheduling software in progress.. | In progress |
| IT Plan | Lecture Capturing System: Scalable and sustainable lecture capture system to be purchased meeting the needs of on/off campus learning. | Fall 2010 | LTS, T&N | RFP being developed. Final phases of the RFP process Vendor invited to campus to dem product in December with potential contract start date in January 2011. | Complete |
| IT Plan | Jarvis Hall Remodel Project: With the remodeling of Jarvis hall, there is a need for coordination and development of a purchase plan for classroom furnishings and classroom technology equipment. | Fall 2010 | LTS, T&N | Most systems complete. A few projectors still need to be installed. Classrooms are complete except for a few document cameras. Meeting rooms in progress. | Complete |
| IT Plan | D2L Course set-up automation: Previously, all courses within D2L (learn@UW) have been populated on a request basis. With the high percentage of courses using D2L, population will be automated. Issues with multi-section and mixed courses need addressing. Other campuses with PeopleSoft Campus Solutions are automating the population of courses and will be consulted with. | Spring 2011 | LTS | Evaluating and coordinating with the Registrar's Office. Programming request submitted and programming in beginning stages. | In progress. Completion slated Fall 2011. |
| IT Plan | D2L Gradebook integration with PeopleSoft: Many UW schools with PeopleSoft campus solutions have the capability of integrating the Gradebook within D2L with PeopleSoft. Learn@UW has the modification and assists campuses in deployment. | Summer 2012 | EIS, LTS | Project on hold per UW System. See PeopleSoft D2L SAIP pilot below. | Project on hold per UW System. Slated to begin summer 2012 |
| IT Plan | Data Center capacity planning or infrastructure.: Cooling and power are becoming issues within the campus server room. Clean electrical power is at or near capacity and cooling issue. Move part of data center somewhere else? Replace older servers with blade servers. | Spring 2011 | GS, T&N | A/E is designing new data center with adequate cooling for campus data systems within Millennium Hall. Small project has been submitted to UW System for funding. A new server room to be constructed in Millennium 327-329. | Small project approved. In initial planning stages with completion January 2012. |
| IT Plan | Project Management Framework--Project Authorization/Development/Execution initiative: Process /create structure/support from management to do IT projects. | Fall 2010 | LIT | Propose a project Management Certificate program for campus staff. No progress as of 12/2010. | No progress as of 5/2/2011 |
| IT Plan | Survey Clearinghouse: Create a survey clearing house to track all campus surveys to reduce duplicate surveys and potentially reduce the number of surveys issued to campus. | Fall 2009 | BPA, T&N | Complete. Custom web application developed using STAR resources. Complete | Complete |
| IT Plan | Student Health Services: Electronic Medical Records. | Spring 2011 | SHS, LIT | RFP released for 3rd party billing system. Records to follow. | In progress |
| IT Plan | Implement T2 Flex: Possible Summer 2009 installation. The Parking Office is looking to provide online all its services from parking permits to fine payment. T2 Flex has been identified as the solution of choice. | Fall 2010 | Parking, T&N | Software in use. In process of incident conversion. Implementing last module for online purchasing of permits spring 2011. | Working on interface. Completion expected Summer 2011. |
| IT Plan | Security Camera System: There are several security camera systems on campus. It is desirable to combine security camera systems to a campus standard as the need for security cameras increases. | Spring 2011 | Campus Police, T&N, Student Life Services | All cameras converted using VideoInsight control software. Complete | Complete |
| IT Plan | Study Abroad Software: The Office of International Education is pursuing StudioAbroad software for efficiencies and more easily provide information to faculty, staff and students. |  | International Education | Complete. | Complete |
| IT Plan | Data Retention of data from Datatel: Various departments on campus have needed to retain storage of records from Datatel for audit and legal purposes. Datatel will remain operational until the UW System implementation of PeopleSoft HRS project is complete. | Fall 2012 | Admiss, BPA, EIS, FA, R&R, SBS | Meeting with campus end users. Each module area will assess needs for data retention and provide specifics as to what is needed to be archived. Will be finalized by the end of 2010 what is needed. Plan will need to be developed for completing the tasks needed. Tentative date of decommissioning Datatel system October 2012. | In progress |
| IT Plan | Data warehouse transition: Explore the possibilities of using data warehouse functionality locally. Oracle expertise resides on campus and there have been several discussions in Madison of discontinuing services. Currently we pay an annual fee to use the service. | Summer 2011 | EIS | Will complete by July 1st, 2011. Project has been submitted. Will need to review tasks that need to be completed and provide timeline. Much of the data is no longer actively being updated since moving to PeopleSoft Campus Solutions. In progress. | In progress |
| IT Plan | Centralized Scheduling: UW-Stout has two scheduling applications: Ad Astra for academic needs and Event Management System for non-academic. By integrating these systems, users can look for facilities from a single source. | 2010 | EIS, SLS | Integration from AdAstra (PeopleSoft Campus Solutions data) to EMS has been completed. Completely implementation of EMS will occur in 2011. Possible implementation of Calendaring option. In progress. Also considering use of EMS for calendaring within web site. Also implementing EMS scheduling software for scheduling DE rooms. | In progress |
| IT Plan | D2L and PeopleSoft integration (SAIP): UW-Stout will be a pilot with other UW campuses to implement the PeopleSoft D2L delivered integration. Will provide real time updates into D2L rosters, classes, and person data. | Summer 2011 | EIS, LTS | Will start project beginning of 2011. Project postponed Until summer 2011. D2L will not be delivering integration until April 2011. Stout is a pilot campus. | Project on hold per UW System. Slated to begin summer 2012 |
| IT Plan | PeopleSoft Campus Solutions PeopleTools 8.5 upgrade: Upgrade to new version released by Oracle. Sunset date for current version of PeopleTools in July 1st, 2011. | Spring 2011 | EIS | Go live date is planned first weekend of January 2011. Upgrade planned for Spring Break 2011. | Upgrade planned for June 2011 |
| IT Plan | Shared Financials System (SFS) and PeopleSoft Campus Solutions general ledger chartfield integration: Implement delivered integration of chartfield data with SFS and PeopleSoft Campus Solutions. Will replace the current Informatica process that is being used. | Fall 2010 | EIS | Implementing Integration Broker configuration. Testing occurring. Testing continuing with one table issue to resolve. | Complete |
| IT Plan | Escholar laptop program and AccessStout: Provide a custom student self-service page in PeopleSoft for eScholar laptop information. Would provide real-time eligibility information, what type of laptop, refresh date, graduation/transfer agreement, etc. | Start in Fall 2010 | SBS, T&N | Researching information to be displayed. Programming request submitted. | In progress |
| IT Plan | Implementation of Runner Technologies address cleansing and standardization software: UW-System has purchased this for the entire UW. This software integrates with PeopleSoft Campus Solutions to cleanse addresses and also provide real time address formatting to meet the USPS standards. | Spring 2011 | EIS | Will need to clean up bad addresses as a result of the cleansing process. This one time activity may be time consuming. Exploring testing online access vs batch in development environment. | In progress |
| IT Plan | Touchnet upgrade: Bill+Payment, Paypath migration and upgrade. This will include eBills for students. | Fall 2010 | EIS, SBS | Implementation has been occurring over the past several months. In progress | Testing |
| IT Plan | PeopleSoft Functionality: Continue to explore additional functionality using existing licensing within PeopleSoft. Supply Chain Management, Training, Travel & expense are possible candidates. | Ongoing | Campus | CSRG will be considering a proposal for Supply Chain Management for fy10. No progress as of 12/2010. | No progress as of 5/2/2011 |
| IT Plan | Purging D2L courses: Improve performance of D2L at System level by purging old courses. When complete only courses 2.5 years or newer will be stored on Learn@UW servers. | Ongoing | UW System, LTS | Second cycle complete. This will be an annual occurrence once courses older than 3 years are purged. Next purge in progress. | In progress |
| IT Plan | Lab Mod: Each year System sets aside a fund of money for each campus to upgrade their laboratory and classroom equipment. The Space committee reviews these proposals and makes a recommendation to the Provost as to which proposals to fund with the amount available. | Ongoing | LTS, Campus Space Committee | The Space Committee review and recommend proposals.. Coordination of projects ongoing with LTS assisting with instructional technology elements. | In progress |
| IT Plan | Mediated Classroom Maintenance: Keeping the Classroom technology operational and effective for instruction. | Ongoing | LTS, T&N | This is an ongoing process to upgrade and make the systems more user friendly. Major upgrades are made during the summer. Replacement schedule created and identified replacement classroom projectors needed. | In progress |
| IT Plan | Provide coordinated assistance to faculty and staff related to learning technology approaches and systems (technology changes, teaching strategies, D2L, software, hardware etc.): Make learning technology materials, processes and info accessible, convenient, and manageable and integrate with other information delivery. | Ongoing | LTS, NTLC | Tutorials have developed with special emphasis on ADA. Assessment of instructional needs and workshop programming offered. Workshops, tutorials, institutes continue to be offered throughout the year in various formats. | In progress |
| IT Plan | Continuously Manage Software Application Licensing: Software companies have become increasingly determined and effective at preventing and detecting illegal use of software applications. Now more than ever we must strictly adhere to license agreements. | Ongoing | T&N | Software Administrator has catalogued all known campus-application license agreements and is producing and increasing available documentation. Departments must provide a copy of a valid license agreement before any application will be installed by T&N. This is a fluid process and will continue to monitor for license compliance. | In progress |
| IT Plan | New Instructor Workshop: Instruction Orientation to Stout teaching with technology. | Ongoing | LTS, NTLC | Complete August 2010. Planning for Fall 2011 in progress. | In progress |
| IT Plan | Prof Dev Week: Opportunity to offer multiple topic workshops for instructors. | Ongoing | LTS, NTLC | Fall 2010 complete; January 2011 in progress. | In progress |
| IT Plan | Facilitate the replacement of faculty/staff computers thereby ensuring that everyone has relatively new and efficient computer equipment: Faculty/staff cannot work efficiently with old, slow computing equipment. | Ongoing | Chancellor | Chancellor provides funding for half of the cost for a new desktop or laptop computer. This is ongoing and will continue with approval of the Chancellor. | In progress |
| IT Plan | Continue campus-wide Key Server Software License Management System: A software license management system allows a number of users to share software licenses, perhaps negating the necessity to purchase copies for each individual user. However, it still only supports the licensed number of users simultaneously, denying access to any additional users over the maximum number. The possibility exists to open software use from the Keyserver to professional staff. | Ongoing | T&N | Ongoing. Each year as new applications and updates are available, the Software Administrator must develop licensing and custom-deployment models for all software packages. A KeyServer software request form has been developed and is available online. License numbers have been adjusted based on usage reporting. This is an ongoing process and changes along with licensing agreements from vendors. | In progress |
| IT Plan | Continue coordination and management of university web-site: Maintain cohesiveness across the university’s online presence, provide customized search results, monitor and maintain site usage statistics, coordinate official content, maintain university brand and identity, design and implementation of site-wide templates, provide consistent navigational design, standards and conventions, planned information architecture, and maintenance and evolution of web publishing guidelines and standards. | Ongoing | EIS, Marketing | Steering group created. Work delegated with clear responsibilities for Marketing and EIS staff. | In progress |
| IT Plan | Implement document imaging solution: The campus direction to a paperless environment would be greatly benefited with imaging. Increased productivity by not filing, retrieving and re-filing paper documents would be realized. Imaging would decrease the need for physical storage of paper documents. Imaging software has the capability of retrieving documents associated with a student or staff ID displayed on a Datatel screen. Workflow capabilities to automate business processes will be included in an imaging package. ImageNow has been selected. | Ongoing | LIT and implementing departments | In progress. As of September 2010, 26 departments are using ImageNow with 3 more slated for implementation. As this solution continues to grow it will require additional resources. Continuing with departments in queue along with adding additional functionality. | In progress |
| IT Plan | Training for CMS: Provide training for departments to manage their own content. | Ongoing | EIS, Marketing | In progress. Hands on workshop offered periodically. | In progress |
| IT Plan | Laptop Transfer Program: A Pilot has started with Spring 2006 that provide a laptop at no cost to qualified graduating seniors in the e-Scholar program. | Ongoing | T&N, SBS | In progress. | In progress |
| IT Plan | Campus Wireless Network Improvement: The campus wireless network has become relied upon to the extent that the service is critical to the University. A campus survey and evaluation of the wireless network will be conducted to cover inadequate areas and improve access across campus. | Ongoing | T&N | Existing buildings will be re-evaluated and adjusted to improve wireless connectivity. Will continue to improve/enhance the campus wireless network. | In progress |
| IT Plan | PeopleSoft Student Information System: UW-System has mandated that all integrated campuses migrate to PeopleSoft financials by July 2007. Following the SFS migration, the campus will also migrate from Datatel to PeopleSoft SIS. | Ongoing | Adm, EIS FA, R&R, SBS | Implementation completed. Continuing upgrades with bundles and patches. Additional modifications have been requested. Cleaning up converted data. Continuing to clean student records. | Complete |
| IT Plan | Work with the Faculty Senate and develop a proposal to address their concerns related to ASK5000 |  | Faculty Senate, LIT | In progress | In progress. Survey complete. Faculty Senate to evaluate |
| IT Plan | Serve on the small group to make recommendations on data queries and training, and implement any recommendations assigned to you. |  |  | See Reporting data Store above. | See Reporting Data Store above. |

55 action items